## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Division | Providing FHTC at Surface Water based Water Supply Scheme (Northern Sector), Part-I, Zone-III within Kaliganj Block (Phase-C) | SM/07435 | Retrofitting | PROVIDING FHTC AT SURFACE BASED W/S SCHEME ATPART-1 Z-3 |  |  | VCH/001065/2020-2021 | 460/DW | 30/03/2021 | 30/03/2021 | M/S NIBHAS SINHA | 50.76 | 0 | 0 | 0
2 | NADIA |  | Nadia Division | Providing FHTC at Surface Water based Water Supply Scheme (Northern Sector), Part-I, Zone-III within Kaliganj Block (Phase-C) | SM/07435 | Retrofitting | PROVIDING FHTC AT SURFACE WATER BASED WATER SUPPLY SCHEME (NORTHERN SECTOR) PART-I, ZONE-III WITHIN KALIGANJ BLOCK (PHASE-C) |  |  | VCH/000909/2020-2021 |  | 17/03/2021 | 17/03/2021 | M/S NIBHAS SINHA | 50.76 | 0 | 0 | 0
3 | NADIA |  | Nadia Division | Providing FHTC at Surface Water based Water Supply Scheme (Northern Sector), Part-I, Zone-III within Kaliganj Block (Phase-C) | SM/07435 | Retrofitting | PROVIDING FHTC SURFCE WATER BASED WATER SUPPLY SCHEME NORTHERN SECTOR , PART-I, Z-III, WITHIN KALIGANJ BLOCK, PHASE-C |  |  | VCH/000876/2021-2022 | 475/PFMS | 03/02/2022 | 03/02/2022 | M/S NIBHAS SINHA | 4.67 | 0 | 0 | 0
4 | NADIA |  | Nadia Division | Providing FHTC at Surface Water based Water Supply Scheme (Northern Sector), Part-I, Zone-III within Kaliganj Block (Phase-C) | SM/07435 | Retrofitting | Providing FHTC at Surface Water Based Water Supply Scheme (Northern Sector) Part-I, Zone-III, within Kaliganj Block (Phase-C, Retrofitting) | Assistant Engineer | Junior Engineer 1 | ORD/000263/2020-2021 | 161/ND | 13/01/2021 | 13/04/2021 | M/S NIBHAS SINHA | 97.11 | 0 | 0 | 0
Total | [13 empty] | 203.31 | 0 | 0