## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Division | Providing FHTC at Surface Water based Water Supply Scheme (Northern Sector), Part-III, Zone-I within Krishnagar & Nabadwip (Part) Block (Phase-A) | SM/07455 | Retrofitting | Providing FHTC at Surface Water based Water Supply Scheme (Northern Sector), Part-III, Zone-I within Krishnagar & Nabadwip (Part) Block (Phase-A). |  |  | VCH/000514/2021-2022 | 163/PFMS | 07/09/2021 | 07/09/2021 | TARUN KUMAR BHATTACHARYA | 93.03 | 0 | 0 | 0
2 | NADIA |  | Nadia Division | Providing FHTC at Surface Water based Water Supply Scheme (Northern Sector), Part-III, Zone-I within Krishnagar & Nabadwip (Part) Block (Phase-A) | SM/07455 | Retrofitting | PROVIDING FHTC AT SURFACE WATER BASED WATER SUPPLY SCHEME NORTHERN SECTOR , PART-III, Z-I, WITHIN KRISHNAGAR AND NABADWIP BLOCK , PHASE-A. |  |  | VCH/000878/2021-2022 | 501/PFMS | 03/02/2022 | 03/02/2022 | M/S R. DUTTA & CO. | 0.45 | 0 | 0 | 0
3 | NADIA |  | Nadia Division | Providing FHTC at Surface Water based Water Supply Scheme (Northern Sector), Part-III, Zone-I within Krishnagar & Nabadwip (Part) Block (Phase-A) | SM/07455 | Retrofitting | Providing FHTC at Surface Water Based Water Supply Scheme (Northern Sector) Part-III, Zone-I, within Krishnagar-II & Nabadwip Block (Phase-A, Retrofitting) | Assistant Engineer |  | ORD/000394/2020-2021 | 770/ND | 10/02/2021 | 11/05/2021 | TARUN KUMAR BHATTACHARYA | 97.09 | 0 | 0 | 0
4 | NADIA |  | Nadia Division | Providing FHTC at Surface Water based Water Supply Scheme (Northern Sector), Part-III, Zone-I within Krishnagar & Nabadwip (Part) Block (Phase-A) | SM/07455 | Retrofitting | Providing additional FHTC in connection with Surface based WSS (Northern Sector) Part-III , Zone I within Krishnagar II & Nabadwip (Part) Block (Phase-A) | Assistant Engineer | Junior Engineer 3 | ORD/000049/2023-2024 | 490/KSD | 25/04/2023 | 10/05/2023 | TARUN KUMAR BHATTACHARYA | 0.96 | 0 | 0 | 90
Total | [13 empty] | 191.54 | 0 | 0