## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Division | Providing Functional House Tap Connection from Bablari Dewanganj Water Supply Scheme under Jal Swapno Programme | SM/07456 | Retrofitting | Providing Functional House Tap Connection from Bablari Dewanganj Water Supply Scheme under Jal Swapno Programme. |  |  | VCH/000991/2020-2021 |  | 24/03/2021 | 24/03/2021 | S.S. ENTERPRISE | 44.96 | 0 | 0 | 0
2 | NADIA |  | Nadia Division | Providing Functional House Tap Connection from Bablari Dewanganj Water Supply Scheme under Jal Swapno Programme | SM/07456 | Retrofitting | Providing Functional House Tap Connection from Bablari Dewanganj Water Supply Scheme under Jal Swapno Programme |  |  | VCH/000467/2021-2022 | 264/PFMS | 08/10/2021 | 08/10/2021 | S.S. ENTERPRISE | 35.02 | 0 | 0 | 0
3 | NADIA |  | Nadia Division | Providing Functional House Tap Connection from Bablari Dewanganj Water Supply Scheme under Jal Swapno Programme | SM/07456 | Retrofitting | PROVIDING FHTC AT BABLARI DEYANGANJ W/S SCHEME UNDER JAL SWAPNO PROGRAM. |  |  | VCH/000204/2021-2022 | 89/PPMS | 15/07/2021 | 15/07/2021 | S.S. ENTERPRISE | 44.96 | 0 | 0 | 0
4 | NADIA |  | Nadia Division | Providing Functional House Tap Connection from Bablari Dewanganj Water Supply Scheme under Jal Swapno Programme | SM/07456 | Retrofitting | Providing functional household tap connection (Part) including supply of 15mm dia PVC pipe of average length of 15 m, 10mm dia Gun-Metal Ferrule, Saddle piece (as required size) 15mm dia Bib cock etc. all complete from Bablari Dewanganj W/S scheme in Nadia District under Nadia Division P.H.E. Dte. | Assistant Engineer |  | ORD/000239/2020-2021 | 44/ND | 06/01/2021 | 06/04/2021 | S.S. ENTERPRISE | 97.07 | 0 | 0 | 100
5 | NADIA |  | Nadia Division | Providing Functional House Tap Connection from Bablari Dewanganj Water Supply Scheme under Jal Swapno Programme | SM/07456 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000015/2021-2022 | 93/ND | 06/01/2022 | 06/01/2022 | Resource Division | 7.71 | 0 | 0 | 0
6 | NADIA |  | Nadia Division | Providing Functional House Tap Connection from Bablari Dewanganj Water Supply Scheme under Jal Swapno Programme | SM/07456 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000095/2021-2022 | 792/ND | 18/02/2022 | 18/02/2022 | Resource Division | 3.71 | 0 | 0 | 0
Total | [13 empty] | 233.42 | 0 | 0