## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Division | Providing FHTC at Surface Water based Water Supply Scheme (Northern Sector), Part-II, Zone-IV within Nakashipara Block (Phase-A) | SM/07457 | Retrofitting | PROVIDING FHTC AT SURFACE BASED W/S SCHEME AT PART-2, Z-4 |  |  | VCH/001074/2020-2021 | 460/DW | 30/03/2021 | 30/03/2021 | H I ENTERPRISE | 72.4 | 0 | 0 | 0
2 | NADIA |  | Nadia Division | Providing FHTC at Surface Water based Water Supply Scheme (Northern Sector), Part-II, Zone-IV within Nakashipara Block (Phase-A) | SM/07457 | Retrofitting | PROVIDING FHTC AT SURFACE WATER BASED WATER SUPPLY SCHEME NORTHERN SECTOR , PART-II, Z-IV, NABADWIP BLOCK, PHASE-A. |  |  | VCH/000880/2021-2022 | 490/PFMS | 03/02/2022 | 03/02/2022 | INDRANIL DUTTA & ASSOCIATES | 0.41 | 0 | 0 | 0
3 | NADIA |  | Nadia Division | Providing FHTC at Surface Water based Water Supply Scheme (Northern Sector), Part-II, Zone-IV within Nakashipara Block (Phase-A) | SM/07457 | Retrofitting | Providing FHTC at Surface Water Based Water Supply Scheme (Northern Sector), Part-II, Zone-IV within Nakashipara Block ( Phase -A) | Assistant Engineer | Junior Engineer 1 | ORD/000285/2020-2021 | 245/ND | 15/01/2021 | 15/04/2021 | H I ENTERPRISE | 97.1 | 18.41 | 18.96 | 0
Total | [13 empty] | 169.91 | 18.41 | 10.83