## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Division | Providing Functional Household Tap Connection from Gazna Water Scheme (for Gazna Mouza) under Jal Swapno Programme | SM/07471 | Retrofitting | PROVIDING FHTC AT SURFACE BASED W/S SCHEME AT GAZNA W/S SCHEME |  |  | VCH/001067/2020-2021 | 460/DW | 30/03/2021 | 30/03/2021 | SANJOY BAKSHI | 12.7 | 0 | 0 | 0
2 | NADIA |  | Nadia Division | Providing Functional Household Tap Connection from Gazna Water Scheme (for Gazna Mouza) under Jal Swapno Programme | SM/07471 | Retrofitting | Providing Functional Household Tap Connection from Gazna Water Scheme (for Gazna Mouza) under Jal Swapno Programme |  |  | VCH/000993/2020-2021 |  | 24/03/2021 | 24/03/2021 | APURBA MANDAL | 34.69 | 0 | 0 | 0
3 | NADIA |  | Nadia Division | Providing Functional Household Tap Connection from Gazna Water Scheme (for Gazna Mouza) under Jal Swapno Programme | SM/07471 | Retrofitting | Providing Functional Household Tap Connection from Gazna Water Scheme (for Gazna Mouza) under Jal Swapno Programme. |  |  | VCH/000994/2020-2021 |  | 24/03/2021 | 24/03/2021 | APURBA MANDAL | 34.35 | 0 | 0 | 0
4 | NADIA |  | Nadia Division | Providing Functional Household Tap Connection from Gazna Water Scheme (for Gazna Mouza) under Jal Swapno Programme | SM/07471 | Retrofitting | Providing Functional Household Tap Connection from Gazna Water Scheme (for Gazna Mouza) under Jal Swapno Programme |  |  | VCH/000942/2021-2022 | 515/PFMS | 03/02/2022 | 03/02/2022 | APURBA MANDAL | 3.12 | 0 | 0 | 0
5 | NADIA |  | Nadia Division | Providing Functional Household Tap Connection from Gazna Water Scheme (for Gazna Mouza) under Jal Swapno Programme | SM/07471 | Retrofitting | Providing functional household tap connection (Part) including supply of 15mm dia PVC pipe of average length of 15 m, 10mm dia Gun-Metal Ferrule, Saddle piece (as required size) 15mm dia Bib cock etc. all complete for Gazna W/S scheme in Nadia District under Nadia Division P.H.E. Dte.PART-C | Assistant Engineer |  | ORD/000348/2020-2021 | 508/ND | 27/01/2021 | 13/03/2021 | APURBA MANDAL | 37.85 | 71.79 | 189.68 | 100
6 | NADIA |  | Nadia Division | Providing Functional Household Tap Connection from Gazna Water Scheme (for Gazna Mouza) under Jal Swapno Programme | SM/07471 | Retrofitting | Providing functional household tap connection (Part) including supply of 15mm dia PVC pipe of average length of 15 m, 10mm dia Gun-Metal Ferrule, Saddle piece (as required size) 15mm dia Bib cock etc. all complete for Gazna W/S scheme in Nadia District under Nadia Division P.H.E. Dte.PART-A | Assistant Engineer |  | ORD/000346/2020-2021 | 506/ND | 27/01/2021 | 13/03/2021 | SANJOY BAKSHI | 13.11 | 0 | 0 | 0
7 | NADIA |  | Nadia Division | Providing Functional Household Tap Connection from Gazna Water Scheme (for Gazna Mouza) under Jal Swapno Programme | SM/07471 | Retrofitting | Providing functional household tap connection (Part) including supply of 15mm dia PVC pipe of average length of 15 m, 10mm dia Gun-Metal Ferrule, Saddle piece (as required size) 15mm dia Bib cock etc. all complete for Gazna W/S scheme in Nadia District under Nadia Division P.H.E. Dte.PART-B | Assistant Engineer |  | ORD/000347/2020-2021 | 507/ND | 27/01/2021 | 13/03/2021 | APURBA MANDAL | 37.85 | 69.39 | 183.33 | 100
8 | NADIA |  | Nadia Division | Providing Functional Household Tap Connection from Gazna Water Scheme (for Gazna Mouza) under Jal Swapno Programme | SM/07471 | Retrofitting | Replacemt of damaged & typically choked UPVC pipe line for augmentation of Ground Water Based Water Supply Scheme for Gazna PWSS of Hanskhali block of Nadia District under Nadia Division P.H.Engineering Dte. (Balance) A- Part. | Assistant Engineer | Junior Engineer 2 | ORD/000370/2023-2024 | 4802/ND | 17/10/2023 | 15/01/2024 | SANDIP BISWAS | 99.5 | 0 | 0 | 96
Total | [13 empty] | 273.16 | 141.18 | 51.68