## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Division | Providing FHTC at Surface Water based Water Supply Scheme (Northern Sector), Part-III, Zone-IV within Krishnagar-II & Nabadwip (Part) Block (Phase-C) | SM/07475 | Retrofitting | PROVIDING FHTC AT SURFACE WATER BASED WATER SUPPLY SCHEME (N/S), PART-III, ZONE-IV, WITHIN KRISHAGAR -II & NABADWIP BLOCK PHASE-C |  |  | VCH/000654/2021-2022 | 304/PFMS | 01/11/2021 | 01/11/2021 | MAHAVIR PUMPS MFG PVT. LTD. | 65 | 0 | 0 | 0
2 | NADIA |  | Nadia Division | Providing FHTC at Surface Water based Water Supply Scheme (Northern Sector), Part-III, Zone-IV within Krishnagar-II & Nabadwip (Part) Block (Phase-C) | SM/07475 | Retrofitting | Providing FHTC at Surface Water Based Water Supply Scheme (Northern Sector) Part-III, Zone-IV, within Krishnagar-II & Nabadwip Block (Phase-C, Retrofitting)" | Assistant Engineer |  | ORD/000402/2020-2021 | 778/ND | 10/02/2021 | 11/05/2021 | MAHABIR PUMPS MFG PVT. LTD. | 97.12 | 0 | 0 | 100
3 | NADIA |  | Nadia Division | Providing FHTC at Surface Water based Water Supply Scheme (Northern Sector), Part-III, Zone-IV within Krishnagar-II & Nabadwip (Part) Block (Phase-C) | SM/07475 | Retrofitting | Scheme Information Board at various water supply schemes under Nadia Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer 2 | ORD/000490/2023-2024 | 283/ND | 11/01/2024 | 11/03/2024 | BIBHAS PAL | 96.01 | 0 | 0 | 81
Total | [13 empty] | 258.12 | 0 | 0