## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Division | Providing FHTC at Surface Water based Water Supply Scheme (Northern Sector), Part-I, Zone-IX within Kaliganj Block (Phase-B) | SM/07476 | Retrofitting | Schedule for laying of pipe line and allied work upto Kaliganj BDO office under Zone-V of Surface Water Based Water Supply Scheme, Nadia District Northern Sector (Part-I) under Debagram Sub Division P.H.E Dte. | Assistant Engineer |  | ORD/000063/2022-2023 | 175/D/DSD | 18/04/2022 | 18/05/2022 | TARUN KUMAR BHATTACHARYA | 2.22 | 2.05 | 92.35 | 0
2 | NADIA |  | Nadia Division | Providing FHTC at Surface Water based Water Supply Scheme (Northern Sector), Part-I, Zone-IX within Kaliganj Block (Phase-B) | SM/07476 | Retrofitting | Providing FHTC at Surface Water Based Water Supply Scheme (Northern Sector) Part-I, Zone-IX within Kaliganj Block (Phase-B) | Assistant Engineer | Junior Engineer 2 | ORD/000090/2021-2022 | 2767/ND | 14/07/2021 | 12/10/2021 | M/S K.P. CONSTRUCTION | 91.11 | 80.29 | 88.12 | 0
3 | NADIA |  | Nadia Division | Providing FHTC at Surface Water based Water Supply Scheme (Northern Sector), Part-I, Zone-IX within Kaliganj Block (Phase-B) | SM/07476 | Retrofitting | Collection of Household data through mobile app for FHTC Connection at following schemes under Nadia Division PHE Dte.Schemes: i) Maidanpur ii) Kulgachhi iii) Monipota iv) Habibpur v) Magurkhali. | Assistant Engineer | Junior Engineer 2 | ORD/000480/2022-2023 | 372/ Kly SD-I | 17/03/2023 | 17/09/2023 | HORIZEN | 4.99 | 1.7 | 34.07 | 10
4 | NADIA |  | Nadia Division | Providing FHTC at Surface Water based Water Supply Scheme (Northern Sector), Part-I, Zone-IX within Kaliganj Block (Phase-B) | SM/07476 | Retrofitting | Scheme Information Board at various water supply schemes under Nadia Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer 2 | ORD/000490/2023-2024 | 283/ND | 11/01/2024 | 11/03/2024 | BIBHAS PAL | 96.01 | 3.43 | 3.57 | 81
Total | [13 empty] | 194.33 | 87.47 | 45.01