## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Division | Providing Functional House Tap Connection from Anand1pur Water Supply Scheme under Jal Swapno Programme (Phase-I) | SM/07486 | Retrofitting | PROVIDING FHTC AT SURFACE BASED W/S SCHEME ATPART-C |  |  | VCH/001066/2020-2021 | 460/DW | 30/03/2021 | 30/03/2021 | JOYGOPAL GUPTI | 18.33 | 0 | 0 | 0
2 | NADIA |  | Nadia Division | Providing Functional House Tap Connection from Anand1pur Water Supply Scheme under Jal Swapno Programme (Phase-I) | SM/07486 | Retrofitting | Providing Functional House Tap Connection from Anand1pur Water Supply Scheme under Jal Swapno Programme (Phase-I) |  |  | VCH/000059/2021-2022 |  | 12/04/2021 | 12/04/2021 | SUBHASIS MAJUMDER | 16.31 | 0 | 0 | 0
3 | NADIA |  | Nadia Division | Providing Functional House Tap Connection from Anand1pur Water Supply Scheme under Jal Swapno Programme (Phase-I) | SM/07486 | Retrofitting | Providing Functional House Tap Connection from Anand1pur Water Supply Scheme under Jal Swapno Programme (Phase-I) |  |  | VCH/000060/2021-2022 |  | 12/04/2021 | 12/04/2021 | BIDYUT KUMAR | 14.57 | 0 | 0 | 0
4 | NADIA |  | Nadia Division | Providing Functional House Tap Connection from Anand1pur Water Supply Scheme under Jal Swapno Programme (Phase-I) | SM/07486 | Retrofitting | PROVIDING FHTC INCLUDING SUPPLY OF 15MM DIA PVC PIPE OF AVERAGE LENGTH OF 15MM 10MM DIA GUN- METAL FERRULE SADDLE PICE AS REQUIRED SIZE 15MM DIA BIB COCK ETC. ALL COMPLETE AT ANANDAPUR W/S SCHEME PHASE-1,PART-A RETROFITTING, UNDER NADIA DIVISION, PHE , DTE. |  |  | VCH/000216/2021-2022 | 76/PPMS | 15/07/2021 | 15/07/2021 | BIDYUT KUMAR | 14.57 | 0 | 0 | 0
5 | NADIA |  | Nadia Division | Providing Functional House Tap Connection from Anand1pur Water Supply Scheme under Jal Swapno Programme (Phase-I) | SM/07486 | Retrofitting | PROVIDING FHTC INCLUDING SUPPLY OF 15MM DIA PVC PIPE OF AVERAGE LENGTH OF 15MM 10MM DIA GUN- METAL FERRULE SADDLE PICE AS REQUIRED SIZE 15MM DIA BIB COCK ETC. ALL COMPLETE AT ANANDAPUR W/S SCHEME PHASE-1 UNDER NADIA DIVISION, PHE , DTE. |  |  | VCH/000211/2021-2022 | 83/PPMS | 15/07/2021 | 15/07/2021 | SUBHASIS MAJUMDER | 16.31 | 0 | 0 | 0
6 | NADIA |  | Nadia Division | Providing Functional House Tap Connection from Anand1pur Water Supply Scheme under Jal Swapno Programme (Phase-I) | SM/07486 | Retrofitting | Providing functional household tap connection (Part) including supply of 15mm dia PVC pipe of average length of 15 m, 10mm dia Gun-Metal Ferrule, Saddle piece (as required size) 15mm dia Bib cock etc. all complete for Anandapur W/S scheme in Nadia District under Nadia Division P.H.E. Dte.(Phase-I Retro fitting)(PART-C) | Assistant Engineer |  | ORD/000324/2020-2021 | 400/ND | 22/01/2021 | 08/03/2021 | JOYGOPAL GUPTI | 32.34 | 2.04 | 6.31 | 0
7 | NADIA |  | Nadia Division | Providing Functional House Tap Connection from Anand1pur Water Supply Scheme under Jal Swapno Programme (Phase-I) | SM/07486 | Retrofitting | Providing functional household tap connection (Part) including supply of 15mm dia PVC pipe of average length of 15 m, 10mm dia Gun-Metal Ferrule, Saddle piece (as required size) 15mm dia Bib cock etc. all complete for Anandapur W/S scheme in Nadia District under Nadia Division P.H.E. Dte.(Phase-I Retro fitting)(PART-B) | Assistant Engineer |  | ORD/000320/2020-2021 | 399/ND | 22/01/2021 | 08/03/2021 | SUBHASIS MAJUMDER | 32.36 | 2.6 | 8.04 | 100
8 | NADIA |  | Nadia Division | Providing Functional House Tap Connection from Anand1pur Water Supply Scheme under Jal Swapno Programme (Phase-I) | SM/07486 | Retrofitting | Providing functional household tap connection (Part) including supply of 15mm dia PVC pipe of average length of 15 m, 10mm dia Gun-Metal Ferrule, Saddle piece (as required size) 15mm dia Bib cock etc. all complete for Anandapur W/S scheme in Nadia District under Nadia Division P.H.E. Dte.(Phase-I Retro fitting)(PART-A) | Assistant Engineer |  | ORD/000319/2020-2021 | 398/ND | 22/01/2021 | 08/03/2021 | BIDYUT KUMAR | 32.35 | 4.03 | 12.45 | 0
9 | NADIA |  | Nadia Division | Providing Functional House Tap Connection from Anand1pur Water Supply Scheme under Jal Swapno Programme (Phase-I) | SM/07486 | Retrofitting | Providing functional household tap connection (Part) including supply of 15mm dia PVC pipe of average length of 15 m, 10mm dia Gun-Metal Ferrule, Saddle piece (as required size) 15mm dia Bib cock etc. all complete for Topla W/S scheme in Nadia District under Nadia Division P.H.E. Dte.(Phase-I Retro fitting)(PART-A) | Assistant Engineer |  | ORD/000330/2020-2021 | 404/ND | 22/01/2021 | 08/03/2021 | NILAY KUMAR BHATTACHARYA | 32.33 | 19.62 | 60.7 | 0
Total | [13 empty] | 209.46 | 28.29 | 13.51