## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Division | Providing Functional House Tap Connection from Sonda (Zone-II) Water Supply Scheme under Jal Swapno Programme (Phase-I) | SM/07487 | Retrofitting | PROVIDING FHTC AT SURFACE BASED W/S SCHEME AT SONDA Z-1 |  |  | VCH/001063/2020-2021 | 459/DW | 30/03/2021 | 30/03/2021 | BIDYUT KUMAR | 17.23 | 0 | 0 | 0
2 | NADIA |  | Nadia Division | Providing Functional House Tap Connection from Sonda (Zone-II) Water Supply Scheme under Jal Swapno Programme (Phase-I) | SM/07487 | Retrofitting | Providing functional household tap connection (Part) including supply of 15mm dia PVC pipe of average length of 15 m, 10mm dia Gun-Metal Ferrule, Saddle piece (as required size) 15mm dia Bib cock etc. all complete from Sonda (Zone-II) W/S scheme in Nadia District under Nadia Division P.H.E. Dte. (Phase-I, Retrofitting) | Assistant Engineer |  | ORD/000214/2020-2021 | 4041/ND | 30/12/2020 | 28/02/2021 | BIDYUT KUMAR | 20.48 | 0 | 0 | 0
3 | NADIA |  | Nadia Division | Providing Functional House Tap Connection from Sonda (Zone-II) Water Supply Scheme under Jal Swapno Programme (Phase-I) | SM/07487 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000093/2021-2022 | 790/ND | 18/02/2022 | 18/02/2022 | Resource Division | 0.3 | 0 | 0 | 0
Total | [13 empty] | 38.01 | 0 | 0