## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Division | Retrofitting of Providing FHTC at Ground Water based Elangi Water Supply Scheme Zone-1(Phase-1) | SM/07489 | Retrofitting | Retrofitting of Providing FHTC at Ground Water based Elangi Water Supply Scheme Zone-1(Phase-1) |  |  | VCH/000494/2022-2023 | 81/PFMS | 13/07/2022 | 13/07/2022 | DIAMOND ENGINEERS CO.OP SOCIETY LTD. | 3.86 | 0 | 0 | 0
2 | NADIA |  | Nadia Division | Retrofitting of Providing FHTC at Ground Water based Elangi Water Supply Scheme Zone-1(Phase-1) | SM/07489 | Retrofitting | Providing functional household tap connection (Part) including supply of 15mm dia PVC pipe of average length of 15 m, 10mm dia Gun-Metal Ferrule, Saddle piece (as required size) 15mm dia Bib cock etc. all complete from Elangi Zone-I W/S scheme (Phase-I) of Rectrofitting in Nadia District under Nadia Division P.H.E. Dte. | Assistant Engineer |  | ORD/000243/2020-2021 | 61/ND | 07/01/2021 | 07/04/2021 | S.K. CONSTRUCTION | 96.72 | 0 | 0 | 100
Total | [13 empty] | 100.57 | 0 | 0