## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Division | Providing FHTC at Ground Water based Senpur Water Supply Scheme within Krishnagar-1 Block (Phase-1) of Retrofitting. | SM/07490 | Retrofitting | PROVIDING FHTC AT SURFACE BASED W/S SCHEME AT SENPUR W/S SCHEME |  |  | VCH/001075/2020-2021 | 460/DW | 30/03/2021 | 30/03/2021 | M/S KALIMATA ENTERPRISE | 67.02 | 0 | 0 | 0
2 | NADIA |  | Nadia Division | Providing FHTC at Ground Water based Senpur Water Supply Scheme within Krishnagar-1 Block (Phase-1) of Retrofitting. | SM/07490 | Retrofitting | Laying of D I Pipe line in place of UPVC pipe including other allied works from OHR to both side of head work site for providing FHTC under Jal Swapna at Subarnabehar w/s scheme under Nadia Division PHED. | Assistant Engineer | Junior Engineer Krishnanagar - I Block | ORD/000065/2022-2023 | 215/PH | 12/07/2022 | 11/08/2022 | SURAJIT KUMAR GHOSH | 4.65 | 0 | 0 | 92
3 | NADIA |  | Nadia Division | Providing FHTC at Ground Water based Senpur Water Supply Scheme within Krishnagar-1 Block (Phase-1) of Retrofitting. | SM/07490 | Retrofitting | Scheme Information Board at various water supply schemes under Nadia Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer 2 | ORD/000490/2023-2024 | 283/ND | 11/01/2024 | 11/03/2024 | BIBHAS PAL | 96.01 | 0 | 0 | 81
4 | NADIA |  | Nadia Division | Providing FHTC at Ground Water based Senpur Water Supply Scheme within Krishnagar-1 Block (Phase-1) of Retrofitting. | SM/07490 | Retrofitting | Providing functional household tap connection (Part) including supply of 15mm dia PVC pipe of average length of 15 m, 10mm dia Gun-Metal Ferrule, Saddle piece (as required size) 15mm dia Bib cock etc. all complete from Senpur W/S scheme (Phase-I) of Rectrofitting in Nadia District under Nadia Division P.H.E. Dte. | Assistant Engineer |  | ORD/000244/2020-2021 | 62/ND | 07/01/2021 | 07/04/2021 | M/S KALIMATA ENTERPRISE | 96.97 | 0 | 0 | 100
Total | [13 empty] | 264.65 | 0 | 0