## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Division | Retrofitting of Providing FHTC at Ground Water based Ber Ramchandrapur Zone-I Water Supply Scheme within Karimpur-I Block (Phase-1) | SM/07492 | Retrofitting | PROVIDING FHTC AT SURFACE BASED W/S SCHEME AT BER-RAM CHANDRAPUR Z-1 |  |  | VCH/001072/2020-2021 | 460/DW | 30/03/2021 | 30/03/2021 | JOY HIND TUBEWELL'S | 40.81 | 0 | 0 | 0
2 | NADIA |  | Nadia Division | Retrofitting of Providing FHTC at Ground Water based Ber Ramchandrapur Zone-I Water Supply Scheme within Karimpur-I Block (Phase-1) | SM/07492 | Retrofitting | Retrofitting of Providing FHTC at Ground Water based Ber Ramchandrapur Zone-I Water Supply Scheme within Karimpur-I Block (Phase-1). |  |  | VCH/000379/2021-2022 | 232/PFMS | 05/10/2021 | 05/10/2021 | MALI CONSTRUCTION | 2.35 | 0 | 0 | 0
3 | NADIA |  | Nadia Division | Retrofitting of Providing FHTC at Ground Water based Ber Ramchandrapur Zone-I Water Supply Scheme within Karimpur-I Block (Phase-1) | SM/07492 | Retrofitting | Providing functional household tap connection (Part) including supply of 15mm dia PVC pipe of average length of 15 m, 10mm dia Gun-Metal Ferrule, Saddle piece (as required size) 15mm dia Bib cock etc. all complete from Ber Ramchandrapur Zone-I W/S scheme (Phase-I) of Rectrofitting in Nadia District under Nadia Division P.H.E. Dte. | Assistant Engineer |  | ORD/000241/2020-2021 | 59/ND | 07/01/2021 | 23/03/2021 | JOY HIND TUBEWELL'S | 55.08 | 0.99 | 1.79 | 100
Total | [13 empty] | 98.23 | 0.99 | 1.01