## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Division | Providing Functional House Tap Connection for Topla Water Supply Scheme under Jal Swapno Programme (Phase-I) | SM/07493 | Retrofitting | Providing Functional House Tap Connection for Topla Water Supply Scheme under Jal Swapno Programme (Phase-I) |  |  | VCH/000070/2021-2022 |  | 16/04/2021 | 16/04/2021 | NILAY KUMAR BHATTACHARYA | 12.07 | 0 | 0 | 0
2 | NADIA |  | Nadia Division | Providing Functional House Tap Connection for Topla Water Supply Scheme under Jal Swapno Programme (Phase-I) | SM/07493 | Retrofitting | PROVIDING FHTC AT SURFACE BASED W/S SCHEME ATTOPLA W/S SCHEME |  |  | VCH/001068/2020-2021 | 460/DW | 30/03/2021 | 30/03/2021 | SOMNATH CHATTERJEE | 18.55 | 0 | 0 | 0
3 | NADIA |  | Nadia Division | Providing Functional House Tap Connection for Topla Water Supply Scheme under Jal Swapno Programme (Phase-I) | SM/07493 | Retrofitting | PROVIDING FHTC INCLUDING SUPPLY OF 15MM DIA PIPE OF AVERAGE LENGTH OF 15MM 10MM DIA GUN-METAL FERRULE ........AT TOPLA W/S SCHEME PHASE-I RETROFITTING |  |  | VCH/000200/2021-2022 | 72/PPMS | 15/07/2021 | 15/07/2021 | SANDIP BISWAS | 9.28 | 0 | 0 | 0
4 | NADIA |  | Nadia Division | Providing Functional House Tap Connection for Topla Water Supply Scheme under Jal Swapno Programme (Phase-I) | SM/07493 | Retrofitting | PROVIDING FHTC INCLUDING SUPPLY OF 15MM DIA PVC PIPE OF AVERAGE LENGTH OF 15MM 10MM DIA GUN-METAL FERRULE SADDLE PICE AS REQUIRED SIZE 15MM DIA BIB COCK ETC ALL COMPLETE AT TOPLA W/S SCHEME UNDER NADIA DIVISION, PHE , DTE . PHASE-1, RETROFITTING PART-B. |  |  | VCH/000201/2021-2022 | 69/PPMS | 15/07/2021 | 15/07/2021 | NILAY KUMAR BHATTACHARYA | 12.07 | 0 | 0 | 0
5 | NADIA |  | Nadia Division | Providing Functional House Tap Connection for Topla Water Supply Scheme under Jal Swapno Programme (Phase-I) | SM/07493 | Retrofitting | Providing Functional House Tap Connection for Topla Water Supply Scheme under Jal Swapno Programme (Phase-I) |  |  | VCH/001023/2021-2022 | 606/PFMS | 11/03/2022 | 11/03/2022 | OTHERS | 11.34 | 0 | 0 | 0
6 | NADIA |  | Nadia Division | Providing Functional House Tap Connection for Topla Water Supply Scheme under Jal Swapno Programme (Phase-I) | SM/07493 | Retrofitting | Providing functional household tap connection (Part) including supply of 15mm dia PVC pipe of average length of 15 m, 10mm dia Gun-Metal Ferrule, Saddle piece (as required size) 15mm dia Bib cock etc. all complete for Topla W/S scheme in Nadia District under Nadia Division P.H.E. Dte.(Phase-I Retro fitting)(PART-C) | Assistant Engineer |  | ORD/000332/2020-2021 | 406/ND | 22/01/2021 | 08/03/2021 | SOMNATH CHATTERJEE | 32.31 | 22.45 | 69.49 | 0
7 | NADIA |  | Nadia Division | Providing Functional House Tap Connection for Topla Water Supply Scheme under Jal Swapno Programme (Phase-I) | SM/07493 | Retrofitting | Providing functional household tap connection (Part) including supply of 15mm dia PVC pipe of average length of 15 m, 10mm dia Gun-Metal Ferrule, Saddle piece (as required size) 15mm dia Bib cock etc. all complete for Topla W/S scheme in Nadia District under Nadia Division P.H.E. Dte.(Phase-I Retro fitting)(PART-A) | Assistant Engineer |  | ORD/000330/2020-2021 | 404/ND | 22/01/2021 | 08/03/2021 | NILAY KUMAR BHATTACHARYA | 32.33 | 0 | 0 | 0
8 | NADIA |  | Nadia Division | Providing Functional House Tap Connection for Topla Water Supply Scheme under Jal Swapno Programme (Phase-I) | SM/07493 | Retrofitting | Providing functional household tap connection (Part) including supply of 15mm dia PVC pipe of average length of 15 m, 10mm dia Gun-Metal Ferrule, Saddle piece (as required size) 15mm dia Bib cock etc. all complete for Topla W/S scheme in Nadia District under Nadia Division P.H.E. Dte.(Phase-I Retro fitting)(PART-B) | Assistant Engineer |  | ORD/000331/2020-2021 | 405/ND | 22/01/2021 | 08/03/2021 | SANDIP BISWAS | 32.33 | 22.61 | 69.95 | 0
Total | [13 empty] | 160.27 | 45.06 | 28.12