## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Division | Providing Functional House Tap Connection from Kulgachi Water Supply Scheme under Jal Swapno Programme | SM/07494 | Retrofitting | Providing Functional House Tap Connection from Kulgachi Water Supply Scheme under Jal Swapno Programme |  |  | VCH/000898/2021-2022 | 534/PFMS | 23/02/2022 | 23/02/2022 | SHYAMAL SHIL | 54.42 | 0 | 0 | 0
2 | NADIA |  | Nadia Division | Providing Functional House Tap Connection from Kulgachi Water Supply Scheme under Jal Swapno Programme | SM/07494 | Retrofitting | Providing functional household tap connection (Part) including supply of 15mm dia PVC pipe of average length of 15 m, 10mm dia Gun-Metal Ferrule, Saddle piece (as required size) 15mm dia Bib cock etc. all complete from Kulgachi W/S scheme in Nadia District under Nadia Division P.H.E. Dte.(Phase-I, Retrofitting) | Assistant Engineer |  | ORD/000238/2020-2021 | 45/ND | 06/01/2021 | 06/04/2021 | SHYAMAL SHIL | 92.07 | 56.93 | 61.83 | 0
3 | NADIA |  | Nadia Division | Providing Functional House Tap Connection from Kulgachi Water Supply Scheme under Jal Swapno Programme | SM/07494 | Retrofitting | Collection of Household data through mobile app for FHTC Connection at following schemes under Nadia Division PHE Dte.Schemes: i) Maidanpur ii) Kulgachhi iii) Monipota iv) Habibpur v) Magurkhali. | Assistant Engineer | Junior Engineer 2 | ORD/000480/2022-2023 | 372/ Kly SD-I | 17/03/2023 | 17/09/2023 | HORIZEN | 4.99 | 0.58 | 11.72 | 10
Total | [13 empty] | 151.47 | 57.51 | 37.97