## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Division | Providing FHTC at Surface Water based Water Supply Scheme (Northern Sector), Part-III, Zone-III within Krishnagar-II, Nabadwip (Part) Block (Phase-B) | SM/07495 | Retrofitting | Providing FHTC at Surface Water based Water Supply Scheme (Northern Sector), Part-III, Zone-III within Krishnagar-II, Nabadwip (Part) Block (Phase-B) |  |  | VCH/000608/2021-2022 | 271/PFMS | 08/10/2021 | 08/10/2021 | UNICON INDIA | 61.22 | 0 | 0 | 0
2 | NADIA |  | Nadia Division | Providing FHTC at Surface Water based Water Supply Scheme (Northern Sector), Part-III, Zone-III within Krishnagar-II, Nabadwip (Part) Block (Phase-B) | SM/07495 | Retrofitting | PROVIDING FHTC AT SURFACE WATER BASED W/S SCHEME NORTHERN SECTOR PART-II, ZONE-III, WITHIN KRISHNAGAR-II AND NABADWIP BLOCK PHASE-B RETROFITTING. |  |  | VCH/000197/2021-2022 | 87/PPMS | 15/07/2021 | 15/07/2021 | UNICON INDIA | 29.58 | 0 | 0 | 0
3 | NADIA |  | Nadia Division | Providing FHTC at Surface Water based Water Supply Scheme (Northern Sector), Part-III, Zone-III within Krishnagar-II, Nabadwip (Part) Block (Phase-B) | SM/07495 | Retrofitting | Providing FHTC at Surface Water Based Water Supply Scheme (Northern Sector) Part-III, Zone-III, within Krishnagar-II & Nabadwip Block (Phase-B, Retrofitting)" | Assistant Engineer |  | ORD/000399/2020-2021 | 775/ND | 10/02/2021 | 11/05/2021 | UNICON INDIA | 97.6 | 0 | 0 | 0
Total | [13 empty] | 188.4 | 0 | 0