## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Division | Providing FHTC at Surface Water Based Water Supply Scheme (Northern Sector), Part-II, Zone-V within Nakashipara Block (Phase-A). | SM/07497 | Retrofitting | Providing FHTC at Surface Water Based Water Supply Scheme (Northern Sector), Part-II, Zone-V within Nakashipara Block (Phase-A). |  |  | VCH/001007/2020-2021 |  | 25/03/2021 | 25/03/2021 | UMWELT ENGINEERS PVT LTD | 59.66 | 0 | 0 | 0
2 | NADIA |  | Nadia Division | Providing FHTC at Surface Water Based Water Supply Scheme (Northern Sector), Part-II, Zone-V within Nakashipara Block (Phase-A). | SM/07497 | Retrofitting | Providing FHTC at Surface Water Based Water Supply Scheme (Northern Sector),Part-II, Zone-V within Nakashipara Block(Phase-A) in Nadia District under Nadia Division P.H.E.Dte.(SL.2) | Assistant Engineer | Junior Engineer 3 | ORD/000465/2020-2021 | 971/ND | 25/02/2021 | 26/05/2021 | UMWELT ENGINEERS PVT LTD | 97 | 85.61 | 88.26 | 0
3 | NADIA |  | Nadia Division | Providing FHTC at Surface Water Based Water Supply Scheme (Northern Sector), Part-II, Zone-V within Nakashipara Block (Phase-A). | SM/07497 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000096/2021-2022 | 818/ND | 18/02/2022 | 18/02/2022 | Resource Division | 4.12 | 0 | 0 | 0
Total | [13 empty] | 160.78 | 85.61 | 53.25