## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Division | Providing FHTC at Surface Water based Water Supply Scheme (Northern Sector), Part-II, Zone-II within Nakashipara Block (Phase-A) | SM/07500 | Retrofitting | Providing FHTC at Surface Water based Water Supply Scheme (Northern Sector), Part-II, Zone-II within Nakashipara Block (Phase-A) |  |  | VCH/000990/2021-2022 | 592/PFMS | 04/03/2022 | 04/03/2022 | MONDAL PRECISION PRIVATE LIMITED | 62.51 | 0 | 0 | 0
2 | NADIA |  | Nadia Division | Providing FHTC at Surface Water based Water Supply Scheme (Northern Sector), Part-II, Zone-II within Nakashipara Block (Phase-A) | SM/07500 | Retrofitting | Providing FHTC at Surface Water based Water Supply Scheme (Northern Sector), Part-II, Zone-II within Nakashipara Block (Phase-A) |  |  | VCH/000924/2021-2022 | 565/PFMS | 25/02/2022 | 25/02/2022 | ROY CHOWDHURY ASSOCIATES | 0.45 | 0 | 0 | 0
3 | NADIA |  | Nadia Division | Providing FHTC at Surface Water based Water Supply Scheme (Northern Sector), Part-II, Zone-II within Nakashipara Block (Phase-A) | SM/07500 | Retrofitting | Providing FHTC at Surface Water Based Water Supply Scheme (Northern Sector), Part-II, Zone-II within Nakashipara Block ( Phase -A) | Assistant Engineer | Junior Engineer 2 | ORD/000282/2020-2021 | 242/ND | 15/01/2021 | 15/04/2021 | MONDAL PRECISION PRIVATE LIMITED | 96.61 | 31.18 | 32.28 | 100
4 | NADIA |  | Nadia Division | Providing FHTC at Surface Water based Water Supply Scheme (Northern Sector), Part-II, Zone-II within Nakashipara Block (Phase-A) | SM/07500 | Retrofitting | Providing FHTC, Supplying, laying of distribution system including with all necessary specials, valves, UPVC/HDPE Pipes, 10 mm gun metal ferrule, saddle piece etc. & Construction of Manifold all complete for Zone- II/B (Northern Sector Part-II) Under Nakashipara Block of Nadia District. | Assistant Engineer | Junior Engineer 3 | ORD/000357/2023-2024 | 4651/ND | 10/10/2023 | 29/09/2025 | SATYABRATA CHAKRABORTY | 484.95 | 0 | 0 | 15
Total | [13 empty] | 644.51 | 31.18 | 4.84