## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Division | Providing FHTC at Surface Water based Water Supply Scheme (Northern Sector), Part-II, Zone-VIII within Nakashipara Block (Phase-A) | SM/07502 | Retrofitting | Providing FHTC at Surface Water based Water Supply Scheme (Northern Sector), Part-II, Zone-VIII within Nakashipara Block (Phase-A) |  |  | VCH/000612/2021-2022 | 281/PFMS | 08/10/2021 | 08/10/2021 | ALOK ENTERPRISE (A UNIT OF SAKET TREXIM PVT. LTD.) | 59.73 | 0 | 0 | 0
2 | NADIA |  | Nadia Division | Providing FHTC at Surface Water based Water Supply Scheme (Northern Sector), Part-II, Zone-VIII within Nakashipara Block (Phase-A) | SM/07502 | Retrofitting | Providing FHTC at Surface Water based Water Supply Scheme (Northern Sector), Part-II, Zone-VIII within Nakashipara Block (Phase-A) |  |  | VCH/000476/2021-2022 |  | 04/10/2021 | 04/10/2021 | ALOK ENTERPRISE (A UNIT OF SAKET TREXIM PVT. LTD.) | 59.73 | 0 | 0 | 0
3 | NADIA |  | Nadia Division | Providing FHTC at Surface Water based Water Supply Scheme (Northern Sector), Part-II, Zone-VIII within Nakashipara Block (Phase-A) | SM/07502 | Retrofitting | Providing FHTC at Surface Water Based Water Supply Scheme (Northern Sector), Part-II, Zone-VIII within Nakashipara Block ( Phase -A) in Nadia District under Nadia Division P.H.E. Dte. SLNo.7 | Assistant Engineer | Junior Engineer 3 | ORD/000468/2020-2021 | 894/ND | 19/02/2021 | 20/05/2021 | ALOKE ENTERPRISE | 97.09 | 0 | 0 | 0
4 | NADIA |  | Nadia Division | Providing FHTC at Surface Water based Water Supply Scheme (Northern Sector), Part-II, Zone-VIII within Nakashipara Block (Phase-A) | SM/07502 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000091/2022-2023 | 4318/ND | 29/09/2022 | 29/09/2022 | Resource Division | 12.46 | 0 | 0 | 0
Total | [13 empty] | 229.02 | 0 | 0