## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Division | Providing FHTC at Surface Water based Water Supply Scheme (Northern Sector), Part-II, Zone-VI within Nakashipara Block (Phase-B) | SM/07504 | Retrofitting | Providing FHTC at Surface Water Based Water Supply Scheme (Northern Sector),Part-II, Zone-VI within Nakashipara Block(Phase-B) in Nadia District under Nadia Division P.H.E.Dte.(SL.5) |  |  | VCH/000744/2021-2022 | 412/PFMS | 21/12/2021 | 21/12/2021 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 89.1 | 0 | 0 | 0
2 | NADIA |  | Nadia Division | Providing FHTC at Surface Water based Water Supply Scheme (Northern Sector), Part-II, Zone-VI within Nakashipara Block (Phase-B) | SM/07504 | Retrofitting | PROVIDING FHTC AT SURFACE WATER BASED WATER SUPPLY SCHEME NORTHERN SECTOR , PART-II, Z-VI, WITHIN NAKASHIPARA BLOCK, PHASE-B. |  |  | VCH/000881/2021-2022 | 494/PFMS | 03/02/2022 | 03/02/2022 | ROY CHOWDHURY ASSOCIATES | 0.73 | 0 | 0 | 0
3 | NADIA |  | Nadia Division | Providing FHTC at Surface Water based Water Supply Scheme (Northern Sector), Part-II, Zone-VI within Nakashipara Block (Phase-B) | SM/07504 | Retrofitting | Providing FHTC at Surface Water Based Water Supply Scheme (Northern Sector),Part-II, Zone-VI within Nakashipara Block(Phase-B) in Nadia District under Nadia Division P.H.E.Dte.(SL.5) | Assistant Engineer | Junior Engineer 3 | ORD/000467/2020-2021 | 970/ND | 25/02/2021 | 26/05/2021 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 97 | 0 | 0 | 100
4 | NADIA |  | Nadia Division | Providing FHTC at Surface Water based Water Supply Scheme (Northern Sector), Part-II, Zone-VI within Nakashipara Block (Phase-B) | SM/07504 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000093/2022-2023 | 4281/ND | 29/09/2022 | 29/09/2022 | Resource Division | 12.5 | 0 | 0 | 0
Total | [13 empty] | 199.33 | 0 | 0