## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Division | Providing FHTC at Surface Water based Water Supply Scheme (Northern Sector), Part-II, Zone-IV within Nakashipara Block (Phase-C) | SM/07505 | Retrofitting | Providing FHTC at Surface Water based Water Supply Scheme (Northern Sector), Part-II, Zone-IV within Nakashipara Block (Phase-C) |  |  | VCH/000483/2021-2022 |  | 04/10/2021 | 04/10/2021 | UMWELT ENGINEERS PVT LTD | 62.5 | 0 | 0 | 0
2 | NADIA |  | Nadia Division | Providing FHTC at Surface Water based Water Supply Scheme (Northern Sector), Part-II, Zone-IV within Nakashipara Block (Phase-C) | SM/07505 | Retrofitting | Providing FHTC at Surface Water based Water Supply Scheme (Northern Sector), Part-II, Zone-IX within Nakashipara Block (Phase-B) |  |  | VCH/000611/2021-2022 | 280/PFMS | 08/10/2021 | 08/10/2021 | UMWELT ENGINEERS PVT LTD | 62.5 | 0 | 0 | 0
3 | NADIA |  | Nadia Division | Providing FHTC at Surface Water based Water Supply Scheme (Northern Sector), Part-II, Zone-IV within Nakashipara Block (Phase-C) | SM/07505 | Retrofitting | Providing FHTC at Surface Water Based Water Supply Scheme (Northern Sector),Part-II, Zone-IV within Nakashipara Block(Phase-C) in Nadia District under Nadia Division P.H.E.Dte.(SL.1) | Assistant Engineer | Junior Engineer 1 | ORD/000466/2020-2021 | 972/ND | 25/02/2021 | 26/05/2021 | UMWELT ENGINEERS PVT LTD | 97 | 27.21 | 28.05 | 0
4 | NADIA |  | Nadia Division | Providing FHTC at Surface Water based Water Supply Scheme (Northern Sector), Part-II, Zone-IV within Nakashipara Block (Phase-C) | SM/07505 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000095/2022-2023 | 4282/ND | 29/09/2022 | 29/09/2022 | Resource Division | 12.52 | 0 | 0 | 0
Total | [13 empty] | 234.52 | 27.21 | 11.6