## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Division | Providing FHTC at Surface Water based Water Supply Scheme (Northern Sector), Part-II, Zone-IV within Nakashipara Block (Phase-C) | SM/07505 | Retrofitting | Providing FHTC at Surface Water based Water Supply Scheme (Northern Sector), Part-II, Zone-IV within Nakashipara Block (Phase-C) |  |  | VCH/000483/2021-2022 |  | 04/10/2021 | 04/10/2021 | UMWELT ENGINEERS PVT LTD | 62.5 | 0 | 0 | 0
2 | NADIA |  | Nadia Division | Providing FHTC at Surface Water based Water Supply Scheme (Northern Sector), Part-II, Zone-IV within Nakashipara Block (Phase-C) | SM/07505 | Retrofitting | Providing FHTC at Surface Water based Water Supply Scheme (Northern Sector), Part-II, Zone-IX within Nakashipara Block (Phase-B) |  |  | VCH/000611/2021-2022 | 280/PFMS | 08/10/2021 | 08/10/2021 | UMWELT ENGINEERS PVT LTD | 62.5 | 0 | 0 | 0
3 | NADIA |  | Nadia Division | Providing FHTC at Surface Water based Water Supply Scheme (Northern Sector), Part-II, Zone-IV within Nakashipara Block (Phase-C) | SM/07505 | Retrofitting | Providing FHTC at Surface Water Based Water Supply Scheme (Northern Sector),Part-II, Zone-IV within Nakashipara Block(Phase-C) in Nadia District under Nadia Division P.H.E.Dte.(SL.1) | Assistant Engineer | Junior Engineer 1 | ORD/000466/2020-2021 | 972/ND | 25/02/2021 | 26/05/2021 | UMWELT ENGINEERS PVT LTD | 97 | 27.21 | 28.05 | 0
4 | NADIA |  | Nadia Division | Providing FHTC at Surface Water based Water Supply Scheme (Northern Sector), Part-II, Zone-IV within Nakashipara Block (Phase-C) | SM/07505 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000095/2022-2023 | 4282/ND | 29/09/2022 | 29/09/2022 | Resource Division | 12.52 | 0 | 0 | 0
5 | NADIA |  | Nadia Division | Providing FHTC at Surface Water based Water Supply Scheme (Northern Sector), Part-II, Zone-IV within Nakashipara Block (Phase-C) | SM/07505 | Retrofitting | Construction of OHR, repair and renovation of staff room, repair of boundary wall, construction of service road and restoration of bituminous road. etc. of Surface Water Based Water Supply Scheme for Zone-IV / C (Northern Sector Part-II) in Nakashipara Block of Nadia District to accomodate FHTC under Nadia Division, P.H.E. Dte. [SM/11842]. | Assistant Engineer | Junior Engineer 3 | ORD/000431/2023-2024 | 5557/ND | 12/12/2023 | 03/12/2025 | APURBA MANDAL | 239.4 | 0 | 0 | 10
Total | [13 empty] | 473.92 | 27.21 | 5.74