## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Division | Providing FHTC at Surface Water based Water Supply Scheme (Northern Sector), Part-II, Zone-I within Nakashipara Block (Phase-B) | SM/07835 | Retrofitting | Providing FHTC at Surface Water based Water Supply Scheme (Northern Sector), Part-II, Zone-I within Nakashipara Block (Phase-B) |  |  | VCH/000066/2021-2022 |  | 12/04/2021 | 12/04/2021 | TARUN KUMAR BHATTACHARYA | 41.39 | 0 | 0 | 0
2 | NADIA |  | Nadia Division | Providing FHTC at Surface Water based Water Supply Scheme (Northern Sector), Part-II, Zone-I within Nakashipara Block (Phase-B) | SM/07835 | Retrofitting | PROVIDING FHTC AT SURFACE WATER BASED W/S SCHEME NORTHERN SECTOR PART-2, ZONE-1 WITHIN NAKASHIPARA BLOCK PHASE-B |  |  | VCH/000195/2021-2022 | 74/PPMS | 15/07/2021 | 15/07/2021 | TARUN KUMAR BHATTACHARYA | 41.39 | 0 | 0 | 0
3 | NADIA |  | Nadia Division | Providing FHTC at Surface Water based Water Supply Scheme (Northern Sector), Part-II, Zone-I within Nakashipara Block (Phase-B) | SM/07835 | Retrofitting | Providing FHTC at Surface Water based Water Supply Scheme (Northern Sector), Part-II, Zone-I within Nakashipara Block (Phase-B) |  |  | VCH/000486/2021-2022 | 283/PFMS | 08/10/2021 | 08/10/2021 | TARUN KUMAR BHATTACHARYA | 31.7 | 0 | 0 | 0
4 | NADIA |  | Nadia Division | Providing FHTC at Surface Water based Water Supply Scheme (Northern Sector), Part-II, Zone-I within Nakashipara Block (Phase-B) | SM/07835 | Retrofitting | Providing FHTC at Surface Water Based Water Supply Scheme (Northern Sector), Part-II, Zone-I within Nakashipara Block ( Phase -B) | Assistant Engineer | Junior Engineer 3 | ORD/000281/2020-2021 | 241/ND | 15/01/2021 | 15/04/2021 | TARUN KUMAR BHATTACHARYA | 96.72 | 17.64 | 18.23 | 0
5 | NADIA |  | Nadia Division | Providing FHTC at Surface Water based Water Supply Scheme (Northern Sector), Part-II, Zone-I within Nakashipara Block (Phase-B) | SM/07835 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000092/2022-2023 | 4305/ND | 29/09/2022 | 29/09/2022 | Resource Division | 12.6 | 0 | 0 | 0
6 | NADIA |  | Nadia Division | Providing FHTC at Surface Water based Water Supply Scheme (Northern Sector), Part-II, Zone-I within Nakashipara Block (Phase-B) | SM/07835 | Retrofitting | Construction of OHR, repair and renovation of staff room, construction of service road and restoration of bituminous road. etc. of Surface Water Based Water Supply Scheme for Zone-I / A (Northern Sector Part-II) in Nakashipara Block of Nadia District to accommodate FHTC under Nadia Division, P.H.E. Dte. [SM/11836]. | Assistant Engineer | Junior Engineer 3 | ORD/000430/2023-2024 | 5556/ND | 12/12/2023 | 10/12/2025 | M/S DIPAK ENTERPRISE, GHOSH PARA,WARD NO-4, KALYANI, NADIA-741235 WEST BENGAL | 150.28 | 0 | 0 | 5
Total | [13 empty] | 374.08 | 17.64 | 4.71