## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Division | Providing Functional House Tap Connection from Paschim Bhatjungla Zone-I Water Supply Scheme under Jal Swapno Programme (Phase-I) Retrofitting in Nadia District | SM/08050 | Retrofitting | Providing Functional House Tap Connection from Paschim Bhatjungla Zone-I Water Supply Scheme under Jal Swapno Programme (Phase-I) Retrofitting in Nadia District |  |  | VCH/000895/2021-2022 | 531/PFMS | 23/02/2022 | 23/02/2022 | M/S SHUBHA ENTERPRISE | 11.19 | 0 | 0 | 0
2 | NADIA |  | Nadia Division | Providing Functional House Tap Connection from Paschim Bhatjungla Zone-I Water Supply Scheme under Jal Swapno Programme (Phase-I) Retrofitting in Nadia District | SM/08050 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000086/2021-2022 | 815/ND | 18/02/2022 | 18/02/2022 | Resource Division | 11 | 0 | 0 | 0
3 | NADIA |  | Nadia Division | Providing Functional House Tap Connection from Paschim Bhatjungla Zone-I Water Supply Scheme under Jal Swapno Programme (Phase-I) Retrofitting in Nadia District | SM/08050 | Retrofitting | Providing functional household tap connection (Part) including supply of 15mm dia PVC pipe of average length of 15 m, 10mm dia Gun-Metal Ferrule, Saddle piece (as required size) 15mm dia Bib cock etc. all complete from Paschim Bhatjangla Zone - I W/S scheme (Phase - I) of Retrofitting in Nadia District under Nadia Division P.H.E. Dte." (PART- C) | Assistant Engineer |  | ORD/000019/2021-2022 | 2153/ND | 21/05/2021 | 05/07/2021 | M/S SHUBHA ENTERPRISE | 10.99 | 0 | 0 | 100
4 | NADIA |  | Nadia Division | Providing Functional House Tap Connection from Paschim Bhatjungla Zone-I Water Supply Scheme under Jal Swapno Programme (Phase-I) Retrofitting in Nadia District | SM/08050 | Retrofitting | Laying of parallel new UPVC pipe line in Sansad-X in Deypara GP opposite Jahangirpur Helipada ground to complte FHTC under Paschim Bhatjungla Zone-I W/S scheme under RWS Nadia Sub-Division, PHE Dte. | Assistant Engineer |  | ORD/000108/2021-2022 | 2908/ND | 23/07/2021 | 21/09/2021 | BIPLAB GUHA | 23.33 | 22.97 | 98.47 | 100
5 | NADIA |  | Nadia Division | Providing Functional House Tap Connection from Paschim Bhatjungla Zone-I Water Supply Scheme under Jal Swapno Programme (Phase-I) Retrofitting in Nadia District | SM/08050 | Retrofitting | Providing functional household tap connection (Part) including supply of 15mm dia PVC pipe of average length of 15 m, 10mm dia Gun-Metal Ferrule, Saddle piece (as required size) 15mm dia Bib cock etc. all complete from Paschim Bhatjangla Zone - I W/S scheme (Phase - I) of Retrofitting in Nadia District under Nadia Division P.H.E. Dte." (PART- B) | Assistant Engineer |  | ORD/000016/2021-2022 | 2152/ND | 21/05/2021 | 20/07/2021 | ORIENT CONSTRUCTION | 42.68 | 19.83 | 46.47 | 100
6 | NADIA |  | Nadia Division | Providing Functional House Tap Connection from Paschim Bhatjungla Zone-I Water Supply Scheme under Jal Swapno Programme (Phase-I) Retrofitting in Nadia District | SM/08050 | Retrofitting | Providing functional household tap connection (Part) including supply of 15mm dia PVC pipe of average length of 15 m, 10mm dia Gun-Metal Ferrule, Saddle piece (as required size) 15mm dia Bib cock etc. all complete from Paschim Bhatjangla Zone - I W/S scheme (Phase - I) of Retrofitting in Nadia District under Nadia Division P.H.E. Dte." (PART- A) | Assistant Engineer |  | ORD/000021/2021-2022 | 2151/ND | 21/05/2021 | 20/07/2021 | BOSE & CO | 42.67 | 32.08 | 75.18 | 100
Total | [13 empty] | 141.86 | 74.88 | 52.79