## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Division | Providing Functional House Tap Connection from Madhpur Water Supply Scheme under Jal Swapno Programme in Nadia District (Phase-I Retrofitting). | SM/08052 | Retrofitting | PROVIDING HOUSE CONNECTION INCLUDING SUPPLY OF 15MM DIA G.I/UPVC PIPE OF AVERAGE LENGTH OF 15 MTR. 10MM DIA GUN-METAL FERRULE, SADDLE PICE (AS REQUIRED SIZE), 15MM DIA BIB COCK ETC ALL COMPLETE AT MADHPUR W/S SCHEME UNDER NADIA DIVISION, PHE DTE (PART-B) |  |  | VCH/000833/2020-2021 |  | 26/02/2021 | 26/02/2021 | CHAKRABORTTI ENTERPRISE | 23.9 | 0 | 0 | 0
2 | NADIA |  | Nadia Division | Providing Functional House Tap Connection from Madhpur Water Supply Scheme under Jal Swapno Programme in Nadia District (Phase-I Retrofitting). | SM/08052 | Retrofitting | PROVIDING HOUSE CONNECTION INCLUDING SUPPLY OF 15MM DIA G.I/UPVC PIPE OF AVERAGE LENGTH OF 15 MTR. 10MM DIA GUN-METAL FERRULE, SADDLE PICE (AS REQUIRED SIZE), 15MM DIA BIB COCK ETC ALL COMPLETE AT MADHPUR W/S SCHEME UNDER NADIA DIVISION, PHE DTE (PART-A) |  |  | VCH/000832/2020-2021 |  | 26/02/2021 | 26/02/2021 | GHOSH ENTERPRISE | 23.95 | 0 | 0 | 0
3 | NADIA |  | Nadia Division | Providing Functional House Tap Connection from Madhpur Water Supply Scheme under Jal Swapno Programme in Nadia District (Phase-I Retrofitting). | SM/08052 | Retrofitting | Madhpur Water Supply Scheme Balance work of FHTC. | Assistant Engineer |  | ORD/000726/2021-2022 | 200/TSD | 14/03/2022 | 24/03/2022 | M/S CHANDIMATA CONSTRUCTION | 4.41 | 0 | 0 | 100
4 | NADIA |  | Nadia Division | Providing Functional House Tap Connection from Madhpur Water Supply Scheme under Jal Swapno Programme in Nadia District (Phase-I Retrofitting). | SM/08052 | Retrofitting | Providing Functional House Tap Connection from Madhpur Water Supply Scheme under Jal Swapno Programme in Nadia District (Phase-I Retrofitting). |  |  | VCH/001019/2021-2022 | 606/PFMS | 11/03/2022 | 11/03/2022 | OTHERS | 4.09 | 0 | 0 | 0
5 | NADIA |  | Nadia Division | Providing Functional House Tap Connection from Madhpur Water Supply Scheme under Jal Swapno Programme in Nadia District (Phase-I Retrofitting). | SM/08052 | Retrofitting | Providing functional household tap connection (Part) including supply of 15mm dia PVC pipe of average length of 15 m, , Saddle piece (as required size) 15mm dia Bib cock etc. all complete for Madhpur W/S scheme in Nadia District under Nadia Division P.H.E. Dte.(Phase-I Retrofitting) | Assistant Engineer |  | ORD/000245/2021-2022 | 5361/ND | 30/09/2021 | 29/11/2021 | M/S CHANDIMATA CONSTRUCTION | 55.05 | 0 | 0 | 0
6 | NADIA |  | Nadia Division | Providing Functional House Tap Connection from Madhpur Water Supply Scheme under Jal Swapno Programme in Nadia District (Phase-I Retrofitting). | SM/08052 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000068/2021-2022 | 801/ND | 18/02/2022 | 18/02/2022 | Resource Division | 4.41 | 0 | 0 | 0
7 | NADIA |  | Nadia Division | Providing Functional House Tap Connection from Madhpur Water Supply Scheme under Jal Swapno Programme in Nadia District (Phase-I Retrofitting). | SM/08052 | Retrofitting | Scheme Information Board at various water supply schemes under Nadia Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer 2 | ORD/000490/2023-2024 | 283/ND | 11/01/2024 | 11/03/2024 | BIBHAS PAL | 96.01 | 0 | 0 | 81
Total | [13 empty] | 211.83 | 0 | 0