## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Division | Providing Functional House Tap Connection from Itla Water Supply Scheme under Jal Swapno Programme in Nadia District (Phase-I Retrofitting). | SM/08053 | Retrofitting | PROVIDING FHTC AT ITLA W/S SCHEME (PHASE-I RETROFITTING). |  |  | VCH/000874/2020-2021 |  | 13/03/2021 | 13/03/2021 | M/S K.P. CONSTRUCTION | 23.03 | 0 | 0 | 0
2 | NADIA |  | Nadia Division | Providing Functional House Tap Connection from Itla Water Supply Scheme under Jal Swapno Programme in Nadia District (Phase-I Retrofitting). | SM/08053 | Retrofitting | PROVIDING FHTC INCLUDING SUPPLY OF 15MM DIA PVC PIPE OF AVERAGE LENGTH OF 15MM 10MM DIA GUN-METAL FERRULE SADDLE PICE AS REQUIRED SIZE 15MM DIA BIB COCK ETC ALL COMPLETE AT ITLA W/S SCHEME UNDER NADIA DIVISION, PHE , DTE . PHASE-1, RETROFITTING PART-B. |  |  | VCH/000202/2021-2022 | 67/PPMS | 15/07/2021 | 15/07/2021 | M/S K.P. CONSTRUCTION | 23.03 | 0 | 0 | 0
3 | NADIA |  | Nadia Division | Providing Functional House Tap Connection from Itla Water Supply Scheme under Jal Swapno Programme in Nadia District (Phase-I Retrofitting). | SM/08053 | Retrofitting | Providing functional household tap connection (Part) including supply of 15mm dia PVC pipe of average length of 15 m, 10mm dia Gun-Metal Ferrule, Saddle piece (as required size) 15mm dia Bib cock etc. all complete from Itla W/S scheme in Nadia District under Nadia Division P.H.E. Dte." (Phase-I, Retrofitting) | Assistant Engineer | Junior Engineer 3 | ORD/000117/2021-2022 | 2992/ND | 29/07/2021 | 27/10/2021 | JOYGOPAL GUPTI | 82.18 | 97.91 | 119.14 | 0
Total | [13 empty] | 128.24 | 97.91 | 76.35