## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Division | Providing Functional House Tap Connection from Subernabehar Water Supply Scheme under Jal Swapno Programme in Nadia District (Phase-I Retrofitting). | SM/08054 | Retrofitting | Providing Functional House Tap Connection from Subernabehar Water Supply Scheme under Jal Swapno Programme in Nadia District (Phase-I Retrofitting). |  |  | VCH/000475/2021-2022 | 288/PFMS | 08/10/2021 | 08/10/2021 | M/S S.S ENTERPRISE | 21.54 | 0 | 0 | 0
2 | NADIA |  | Nadia Division | Providing Functional House Tap Connection from Subernabehar Water Supply Scheme under Jal Swapno Programme in Nadia District (Phase-I Retrofitting). | SM/08054 | Retrofitting | PROVIDING FHTC AT SURFACE WATER BASED WATER SUPPLY AT SUBERNABIHAR W/S , PHASE-1 |  |  | VCH/000885/2021-2022 | 482/PFMS | 03/02/2022 | 03/02/2022 | SHYAMAL SHIL | 3.94 | 0 | 0 | 0
3 | NADIA |  | Nadia Division | Providing Functional House Tap Connection from Subernabehar Water Supply Scheme under Jal Swapno Programme in Nadia District (Phase-I Retrofitting). | SM/08054 | Retrofitting | Providing functional household tap connection (Part) including supply of 15mm dia PVC pipe of average length of 15 m, 10mm dia Gun-Metal Ferrule, Saddle piece (as required size) 15mm dia Bib cock etc. all complete from Subarnabehar W/S scheme (Phase - I) of Retrofitting in Nadia District under Nadia Division P.H.E. Dte." (PART- A) | Assistant Engineer |  | ORD/000018/2021-2022 | 2159/ND | 21/05/2021 | 20/07/2021 | M/S S.S ENTERPRISE | 42.27 | 0 | 0 | 0
4 | NADIA |  | Nadia Division | Providing Functional House Tap Connection from Subernabehar Water Supply Scheme under Jal Swapno Programme in Nadia District (Phase-I Retrofitting). | SM/08054 | Retrofitting | Route survey, Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by retrofitting under Jal Swapna for Subarnabehar W/S Scheme in Krishnagar - I Block of Nadia District under Nadia Division. PART - B | Assistant Engineer |  | ORD/000317/2021-2022 | 1190/PH | 03/12/2021 | 13/12/2021 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 1.69 | 0 | 0 | 100
5 | NADIA |  | Nadia Division | Providing Functional House Tap Connection from Subernabehar Water Supply Scheme under Jal Swapno Programme in Nadia District (Phase-I Retrofitting). | SM/08054 | Retrofitting | Laying of D I Pipe line in place of UPVC pipe including other allied works from OHR to both side of head work site for providing FHTC under Jal Swapna at Subarnabehar w/s scheme under Nadia Division PHED. | Assistant Engineer | Junior Engineer Krishnanagar - I Block | ORD/000065/2022-2023 | 215/PH | 12/07/2022 | 11/08/2022 | SURAJIT KUMAR GHOSH | 4.65 | 0 | 0 | 92
6 | NADIA |  | Nadia Division | Providing Functional House Tap Connection from Subernabehar Water Supply Scheme under Jal Swapno Programme in Nadia District (Phase-I Retrofitting). | SM/08054 | Retrofitting | Providing functional household tap connection (Part) including supply of 15mm dia PVC pipe of average length of 15 m, 10mm dia Gun-Metal Ferrule, Saddle piece (as required size) 15mm dia Bib cock etc. all complete from Subarnabehar W/S scheme (Phase - I) of Retrofitting in Nadia District under Nadia Division P.H.E. Dte." (PART- B) | Assistant Engineer |  | ORD/000063/2021-2022 | 2432/ND | 14/06/2021 | 13/08/2021 | SANJOY BAKSHI | 42.57 | 30 | 70.49 | 100
7 | NADIA |  | Nadia Division | Providing Functional House Tap Connection from Subernabehar Water Supply Scheme under Jal Swapno Programme in Nadia District (Phase-I Retrofitting). | SM/08054 | Retrofitting | Providing functional household tap connection (Part) including supply of 15mm dia PVC pipe of average length of 15 m, 10mm dia Gun-Metal Ferrule, Saddle piece (as required size) 15mm dia Bib cock etc. all complete from Subarnabehar W/S scheme (Phase - I) of Retrofitting in Nadia District under Nadia Division P.H.E. Dte." (PART- C) | Assistant Engineer |  | ORD/000017/2021-2022 | 2391/ND | 10/06/2021 | 25/07/2021 | ROY CONSTRUCTION | 9.03 | 8.14 | 90.18 | 100
Total | [13 empty] | 125.69 | 38.15 | 30.35