## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Division | Providing Functional House Tap Connection from Dakshin Jhikipota Zone-I Water Supply Scheme under Jal Swapno Programme in Nadia District (Phase-I Retrofitting). | SM/08056 | Retrofitting | Providing functional household tap connection (Part) including supply of 15mm dia PVC pipe of average length of 15 m, 10mm dia Gun-Metal Ferrule, Saddle piece (as required size) 15mm dia Bib cock etc. all complete from Dakshin Jhitkipota Zone - I W/S scheme (Phase - I) of Retrofitting in Nadia District under Nadia Division P.H.E. Dte." (PART- A) | Assistant Engineer |  | ORD/000010/2021-2022 | 2051/ND | 13/05/2021 | 12/07/2021 | DIAMOND ENGINEERS CO.OP SOCIETY LTD. | 41.49 | 0 | 0 | 100
2 | NADIA |  | Nadia Division | Providing Functional House Tap Connection from Dakshin Jhikipota Zone-I Water Supply Scheme under Jal Swapno Programme in Nadia District (Phase-I Retrofitting). | SM/08056 | Retrofitting | Providing functional household tap connection (Part) including supply of 15mm dia PVC pipe of average length of 15 m, 10mm dia Gun-Metal Ferrule, Saddle piece (as required size) 15mm dia Bib cock etc. all complete from Dakshin Jhitkipota Zone - I W/S scheme (Phase - I) of Retrofitting in Nadia District under Nadia Division P.H.E. Dte." (PART- B) | Assistant Engineer |  | ORD/000013/2021-2022 | 2049/ND | 13/05/2021 | 12/07/2021 | S.K. CONSTRUCTION | 43.81 | 0 | 0 | 100
3 | NADIA |  | Nadia Division | Providing Functional House Tap Connection from Dakshin Jhikipota Zone-I Water Supply Scheme under Jal Swapno Programme in Nadia District (Phase-I Retrofitting). | SM/08056 | Retrofitting | laying of distribution pipe line 125 mm dia UPVC pipe etc. for Providing functional household tap connection at Dakhin Jhitkipota zone- I W/S scheme under Nadia Division PHED. | Assistant Engineer | Junior Engineer Krishnanagar - I Block | ORD/000064/2022-2023 | 214/PH | 12/07/2022 | 11/08/2022 | TAPU SAHA | 4.2 | 0 | 0 | 100
4 | NADIA |  | Nadia Division | Providing Functional House Tap Connection from Dakshin Jhikipota Zone-I Water Supply Scheme under Jal Swapno Programme in Nadia District (Phase-I Retrofitting). | SM/08056 | Retrofitting | Providing functional household tap connection (Part) including supply of 15mm dia PVC pipe of average length of 15 m, 10mm dia Gun-Metal Ferrule, Saddle piece (as required size) 15mm dia Bib cock etc. all complete from Dakshin Jhitkipota Zone - I W/S scheme (Phase - I) of Retrofitting in Nadia District under Nadia Division P.H.E. Dte." (PART- C) | Assistant Engineer |  | ORD/000107/2021-2022 | 2912/ND | 23/07/2021 | 06/09/2021 | PAPAN ROY | 8.8 | 0 | 0 | 100
Total | [13 empty] | 98.3 | 0 | 0