## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Division | Providing Functional Household Tap Connection from Monipota Water Scheme (for Bishnupur & Raotara Mouzas) under Jal Swapno Programme in Nadia District | SM/08125 | Retrofitting | Providing functional household tap connection (Part) including supply of 15mm dia PVC pipe of average length of 15 m, 10mm dia Gun-Metal Ferrule, Saddle piece (as required size) 15mm dia Bib cock etc. all complete for Monipota W/S scheme(for Bishnupur and Raotara Mouza) in Nadia District under Nadia Division P.H.E. Dte. | Assistant Engineer |  | ORD/000026/2021-2022 | 2190/ND | 24/05/2021 | 22/08/2021 | PROJECT INDIA | 92.56 | 0 | 0 | 100
2 | NADIA |  | Nadia Division | Providing Functional Household Tap Connection from Monipota Water Scheme (for Bishnupur & Raotara Mouzas) under Jal Swapno Programme in Nadia District | SM/08125 | Retrofitting | Providing functional household tap connection (Part) including supply of 15mm dia PVC pipe of average length of 15 m, 10mm dia Gun-Metal Ferrule, Saddle piece (as required size) 15mm dia Bib cock etc. all complete for Monipota W/S scheme(for Bishnupur and Raotara Mouza) in Nadia District under Nadia Division P.H.E. Dte. |  |  | VCH/000747/2021-2022 | 350/PFMS | 08/12/2021 | 08/12/2021 | PROJECT INDIA | 92.59 | 0 | 0 | 0
3 | NADIA |  | Nadia Division | Providing Functional Household Tap Connection from Monipota Water Scheme (for Bishnupur & Raotara Mouzas) under Jal Swapno Programme in Nadia District | SM/08125 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000090/2022-2023 | 4332/ND | 29/09/2022 | 29/09/2022 | Resource Division | 8.13 | 0 | 0 | 0
Total | [13 empty] | 193.27 | 0 | 0