## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Division | Providing Functional Household Tap Connection from Madhugari Water Scheme Phase -I of Retrofitting under Jal Swapno Programme in Nadia District | SM/08127 | Retrofitting | Providing functional household tap connection (Part) including supply of 15mm dia PVC pipe of average length of 15 m, 10mm dia Gun-Metal Ferrule, Saddle piece (as required size) 15mm dia Bib cock etc. all complete from Madhugari W/S scheme (Phase - I) of Retrofitting in Nadia District under Nadia Division P.H.E. Dte."(PART- B) | Assistant Engineer |  | ORD/000025/2021-2022 | 2158/ND | 21/05/2021 | 05/07/2021 | M/S KRISHNA MONDAL | 21.21 | 0 | 0 | 0
2 | NADIA |  | Nadia Division | Providing Functional Household Tap Connection from Madhugari Water Scheme Phase -I of Retrofitting under Jal Swapno Programme in Nadia District | SM/08127 | Retrofitting | Providing functional household tap connection (Part) including supply of 15mm dia PVC pipe of average length of 15 m, 10mm dia Gun-Metal Ferrule, Saddle piece (as required size) 15mm dia Bib cock etc. all complete from Madhugari W/S scheme (Phase - I) of Retrofitting in Nadia District under Nadia Division P.H.E. Dte." (PART- A) | Assistant Engineer |  | ORD/000024/2021-2022 | 2157/ND | 21/05/2021 | 05/07/2021 | M/S KRISHNA MONDAL | 21.2 | 0 | 0 | 100
3 | NADIA |  | Nadia Division | Providing Functional Household Tap Connection from Madhugari Water Scheme Phase -I of Retrofitting under Jal Swapno Programme in Nadia District | SM/08127 | Retrofitting | Detailed study of Households/Habitations of Chhota Naldaha, Chilakhali, Chupria, Maheshpur, Nutangram, Pumlia, Sahebnagar, Tehatta, Uttampur and Teinpur Villages under Nadia District under the jurisdiction of Nadia Division, PHE Dte. | Assistant Engineer | Junior Engineer 2 | ORD/000403/2023-2024 | 1209/KLYSD-I | 17/11/2023 | 02/12/2023 | TECHVISION | 2.79 | 0 | 0 | 100
4 | NADIA |  | Nadia Division | Providing Functional Household Tap Connection from Madhugari Water Scheme Phase -I of Retrofitting under Jal Swapno Programme in Nadia District | SM/08127 | Retrofitting | Scheme Information Board at various water supply schemes under Nadia Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer 2 | ORD/000490/2023-2024 | 283/ND | 11/01/2024 | 11/03/2024 | BIBHAS PAL | 96.01 | 0 | 0 | 81
Total | [13 empty] | 141.21 | 0 | 0