## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Central Drilling | Providing Functional Household Tap Connection from Fazilnagar Water Scheme under Jal Swapno Programme in Nadia District | SM/08129 | Retrofitting | PROVIDING 300MM NOMINAL DIA UPVC PIPE CONFORMING TO IS: 12818:2010 & OTHER MATERIALS AT SITE FOR CONSTRUCTION OF TUBE WELL AT KISHOREPUR W/S (REPLACEMENT TW-HW), KARIMPUR II BLOCK UNDER NADIA DISTRICT, CMSD-II (D), CDD, PHE DTE. |  |  | ORD/000067/2022-2023 | 283/CMSD-II (D) | 01/06/2022 | 16/06/2022 | DEV ENTERPRISE | 4.39 | 0 | 0 | 0
2 | NADIA |  | Central Drilling | Providing Functional Household Tap Connection from Fazilnagar Water Scheme under Jal Swapno Programme in Nadia District | SM/08129 | Retrofitting | PROVIDING 200MM NOMINAL DIA UPVC PIPE CONFORMING TO IS: 12818:2010 & OTHER MATERIALS AT SITE FOR CONSTRUCTION OF TUBE WELL AT UTTAR TAJPUR W/S SCHEME (REPLACEMENT TW-II), KARIMPUR-I BLOCK UNDER NADIA DISTRICT, CMSD-II (D), CDD, PHE DTE. |  |  | ORD/000068/2022-2023 | 286/CMSD-II (D) | 01/06/2022 | 16/06/2022 | DEV ENTERPRISE | 4.44 | 0 | 0 | 0
3 | NADIA |  | Central Drilling | Providing Functional Household Tap Connection from Fazilnagar Water Scheme under Jal Swapno Programme in Nadia District | SM/08129 | Retrofitting | SUPPLY & DELIVERY OF PEA SIZE GRAVELS AND BENTONITE POWDER BASED & OTHER MATERIALS AT SITE FOR CONSTRUCTION OF TUBE WELL AT FAZILNAGAR W/S (REPLACEMENT TW-II) IN KARIMPUR-II BLOCK UNDER NADIA DISTRICT UNDER CMSD-II (D), CDD, PHE DTE. |  |  | ORD/000069/2022-2023 | 277/CMSD-II (D) | 01/06/2022 | 16/06/2022 | DEV ENTERPRISE | 2.07 | 0 | 0 | 0
4 | NADIA |  | Central Drilling | Providing Functional Household Tap Connection from Fazilnagar Water Scheme under Jal Swapno Programme in Nadia District | SM/08129 | Retrofitting | PROVIDING DRILLING CREWS & OTHER MATERIALS FOR CONSTRUCTION OF TUBE WELL (300MM X 200MM X 250 MTRS DEPTH) BY DEPARTMENTAL RIG MACHINE FOR UTTAR TAJPUR W/S SCHEME (REPLACEMENT TW-II), KARIMPUR-I BLOCK UNDER NADIA DISTRICT, CMSD-II (D), CDD, PHE DTE. |  |  | ORD/000070/2022-2023 | 284/CMSD-II (D) | 01/06/2022 | 16/06/2022 | DEV ENTERPRISE | 3.52 | 0 | 0 | 0
5 | NADIA |  | Central Drilling | Providing Functional Household Tap Connection from Fazilnagar Water Scheme under Jal Swapno Programme in Nadia District | SM/08129 | Retrofitting | PROVIDING 200MM NOMINAL DIA UPVC PIPE CONFORMING TO IS: 12818:2010 & OTHER MATERIALS AT SITE FOR CONSTRUCTION OF TUBE WELL AT UTTAR TAJPUR W/S SCHEME (REPLACEMENT TW-II), KARIMPUR-I BLOCK UNDER NADIA DISTRICT, CMSD-II (D), CDD, PHE DTE. | Driller In Charge | Junior Engineer | ORD/000071/2022-2023 | 286/CMSD-II(D) | 01/06/2022 | 16/06/2022 | DEY ENTERPRISE | 4.44 | 1.1 | 24.79 | 0
6 | NADIA |  | Central Drilling | Providing Functional Household Tap Connection from Fazilnagar Water Scheme under Jal Swapno Programme in Nadia District | SM/08129 | Retrofitting | PROVIDING 300 MM NOMINAL DIA UPVC PIPE CONFORMING TO IS: 12818:2010 & OTHER MATERIALS AT SITE FOR CONSTRUCTION OF TUBE WELL AT KISHOREPUR W/S (REPLACEMENT TW-HW), KARIMPUR -II BLOCK UNDER NADIA DISTRICT, CMSD-II (D), CDD, PHE DTE. | Driller In Charge | Junior Engineer | ORD/000074/2022-2023 | 283/CMSD-II(D) | 01/06/2022 | 16/06/2022 | DEY ENTERPRISE | 4.39 | 3.94 | 89.79 | 0
7 | NADIA |  | Central Drilling | Providing Functional Household Tap Connection from Fazilnagar Water Scheme under Jal Swapno Programme in Nadia District | SM/08129 | Retrofitting | PROVIDING DRILLING CREWS & OTHER MATERIALS FOR CONSTRUCTION OF TUBE WELL (300MM X 200MM X 250 MTRS DEPTH) BY DEPARTMENTAL RIG MACHINE FOR UTTAR TAJPUR W/S SCHEME (REPLACEMENT TW-II), KARIMPUR-I BLOCK UNDER NADIA DISTRICT, CMSD-II (D), CDD, PHE DTE. | Driller In Charge | Junior Engineer | ORD/000073/2022-2023 | 284/CMSD-II(D) | 01/06/2022 | 16/06/2022 | DEY ENTERPRISE | 3.52 | 3.52 | 100 | 0
8 | NADIA |  | Central Drilling | Providing Functional Household Tap Connection from Fazilnagar Water Scheme under Jal Swapno Programme in Nadia District | SM/08129 | Retrofitting | SUPPLY & DELIVERY OF PEA SIZE GRAVELS AND BENTONITE POWDER SODIUM BASED & OTHER MATERIALS AT SITE FOR CONSTRUCTION OF TUBE WELL AT FAZILNAGAR W/S (REPLACEMENT TW-II) IN KARIMPUR--II BLOCK UNDER NADIA DISTRICT UNDER CMSD-II (D), CDD, PHE DTE. | Driller In Charge | Junior Engineer | ORD/000072/2022-2023 | 277/CMSD-II(D) | 01/06/2022 | 16/06/2022 | DEY ENTERPRISE | 2.07 | 1.63 | 78.79 | 0
9 | NADIA |  | Nadia Division | Providing Functional Household Tap Connection from Fazilnagar Water Scheme under Jal Swapno Programme in Nadia District | SM/08129 | Retrofitting | Providing functional household tap connection (Part) including supply of 15mm dia PVC pipe of average length of 15 m, 10mm dia Gun-Metal Ferrule, Saddle piece (as required size) 15mm dia Bib cock etc. all complete from Fazilnagar W/S scheme (Phase - I) of Retrofitting in Nadia District under Nadia Division P.H.E. Dte." (PART- A) | Assistant Engineer |  | ORD/000023/2021-2022 | 2155/ND | 21/05/2021 | 20/07/2021 | A.P. POWER & CONCRETE | 42.43 | 32.04 | 75.51 | 100
10 | NADIA |  | Nadia Division | Providing Functional Household Tap Connection from Fazilnagar Water Scheme under Jal Swapno Programme in Nadia District | SM/08129 | Retrofitting | Providing functional household tap connection (Part) including supply of 15mm dia PVC pipe of average length of 15 m, 10mm dia Gun-Metal Ferrule, Saddle piece (as required size) 15mm dia Bib cock etc. all complete from Fazilnagar W/S scheme (Phase - I) of Retrofitting in Nadia District under Nadia Division P.H.E. Dte." (PART- C) | Assistant Engineer |  | ORD/000112/2021-2022 | 2930/ND | 26/07/2021 | 09/09/2021 | TULIP ENGINEER'S CO-OP SOCIETY LTD | 7.58 | 6.37 | 84.05 | 0
11 | NADIA |  | Central Drilling | Providing Functional Household Tap Connection from Fazilnagar Water Scheme under Jal Swapno Programme in Nadia District | SM/08129 | Retrofitting | MISCELLANEOUS REPAIRING OF KORES/DR/1000 (MP09GF2033) AND SUPPORT TRUCK (WMK4719) UNDER CMSD-II (D), CDD, PHE DTE. |  |  | ORD/000239/2021-2022 | 161/CMSD-II (D) | 07/07/2021 | 22/07/2021 | CHAKRABORTY MINING & ENGINEERING | 0.75 | 0.75 | 100 | 0
12 | NADIA |  | Central Drilling | Providing Functional Household Tap Connection from Fazilnagar Water Scheme under Jal Swapno Programme in Nadia District | SM/08129 | Retrofitting | REPAIRING OF MUD PUMP FLUID CHAMBER, TRANSMISSION LINE AND OTHERS WORKS ALONG WITH SUPPLY OF DRILLING ACCESSORYU OF RIG MACHINE- JOHN/DR/1500-III UNDER CMSD-I (D), CDD, PHE DTE. |  |  | ORD/000273/2021-2022 | 72/CMSD-I | 30/03/2022 | 14/04/2022 | PADMA ENGINEERING & CO. | 4 | 0.83 | 20.71 | 0
13 | NADIA |  | Central Drilling | Providing Functional Household Tap Connection from Fazilnagar Water Scheme under Jal Swapno Programme in Nadia District | SM/08129 | Retrofitting | Providing Drilling crew and other allied works for construction of Tube well (300mm x 200mm x 210 mtrs. Depth) by utilising Departmental machineries for baidyapur W/S Scheme, Tarakeswar block under hooghly District, CDD PHE Dte. | Driller In Charge | Junior Engineer | ORD/000433/2022-2023 | 1724/CDD | 29/12/2022 | 28/01/2023 | DEY ENTERPRISE | 13.83 | 0.23 | 1.66 | 0
14 | NADIA |  | Nadia Division | Providing Functional Household Tap Connection from Fazilnagar Water Scheme under Jal Swapno Programme in Nadia District | SM/08129 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000098/2021-2022 | 1016/ND | 03/03/2022 | 03/03/2022 | Resource Division | 15.9 | 0 | 0 | 0
15 | NADIA |  | Nadia Division | Providing Functional Household Tap Connection from Fazilnagar Water Scheme under Jal Swapno Programme in Nadia District | SM/08129 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000014/2022-2023 | 3302/ND | 27/07/2022 | 27/07/2022 | Resource Division | 17.79 | 0 | 0 | 0
16 | NADIA |  | Nadia Division | Providing Functional Household Tap Connection from Fazilnagar Water Scheme under Jal Swapno Programme in Nadia District | SM/08129 | Retrofitting | Providing functional household tap connection (Part) including supply of 15mm dia PVC pipe of average length of 15 m, 10mm dia Gun-Metal Ferrule, Saddle piece (as required size) 15mm dia Bib cock etc. all complete from Fazilnagar W/S scheme (Phase - I) of Retrofitting in Nadia District under Nadia Division P.H.E. Dte."(PART- B) | Assistant Engineer |  | ORD/000022/2021-2022 | 2156/ND | 21/05/2021 | 20/07/2021 | IJABUL SK. | 42.68 | 61.87 | 144.94 | 100
Total | [13 empty] | 173.79 | 112.27 | 64.6