## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Division | Providing Functional House Tap Connection from Paschim Bhatjungla Zone-II Water Supply Scheme under Jal Swapno Programme (Phase-I) Retrofitting in Nadia District | SM/08132 | Retrofitting | Providing Functional House Tap Connection from Paschim Bhatjungla Zone-II Water Supply Scheme under Jal Swapno Programme (Phase-I) Retrofitting in Nadia District |  |  | VCH/000474/2021-2022 | 292/PFMS | 08/10/2021 | 08/10/2021 | JAGANNATH ENTERPRISE | 19.98 | 0 | 0 | 0
2 | NADIA |  | Nadia Division | Providing Functional House Tap Connection from Paschim Bhatjungla Zone-II Water Supply Scheme under Jal Swapno Programme (Phase-I) Retrofitting in Nadia District | SM/08132 | Retrofitting | Providing functional household tap connection (Part) including supply of 15mm dia PVC pipe of average length of 15 m, 10mm dia Gun-Metal Ferrule, Saddle piece (as required size) 15mm dia Bib cock etc. all complete from Paschim Bhatjangla Zone - II W/S scheme (Phase - I) of Retrofitting in Nadia District under Nadia Division P.H.E. Dte." (PART- B) | Assistant Engineer |  | ORD/000067/2021-2022 | 2431/ND | 14/06/2021 | 13/08/2021 | JAGANNATH ENTERPRISE | 33.43 | 8.56 | 25.62 | 0
3 | NADIA |  | Nadia Division | Providing Functional House Tap Connection from Paschim Bhatjungla Zone-II Water Supply Scheme under Jal Swapno Programme (Phase-I) Retrofitting in Nadia District | SM/08132 | Retrofitting | Providing functional household tap connection (Part) including supply of 15mm dia PVC pipe of average length of 15 m, 10mm dia Gun-Metal Ferrule, Saddle piece (as required size) 15mm dia Bib cock etc. all complete from Paschim Bhatjangla Zone - II W/S scheme (Phase - I) of Retrofitting in Nadia District under Nadia Division P.H.E. Dte."(PART- C) | Assistant Engineer |  | ORD/000114/2021-2022 | 2957/ND | 27/07/2021 | 10/09/2021 | CHOWDHURY & CO. | 8.82 | 7.41 | 83.96 | 100
4 | NADIA |  | Nadia Division | Providing Functional House Tap Connection from Paschim Bhatjungla Zone-II Water Supply Scheme under Jal Swapno Programme (Phase-I) Retrofitting in Nadia District | SM/08132 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000011/2021-2022 | 100/ND | 06/01/2022 | 06/01/2022 | Resource Division | 1.77 | 0 | 0 | 0
5 | NADIA |  | Nadia Division | Providing Functional House Tap Connection from Paschim Bhatjungla Zone-II Water Supply Scheme under Jal Swapno Programme (Phase-I) Retrofitting in Nadia District | SM/08132 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000089/2021-2022 | 786/ND | 18/02/2022 | 18/02/2022 | Resource Division | 1.08 | 0 | 0 | 0
6 | NADIA |  | Nadia Division | Providing Functional House Tap Connection from Paschim Bhatjungla Zone-II Water Supply Scheme under Jal Swapno Programme (Phase-I) Retrofitting in Nadia District | SM/08132 | Retrofitting | Providing functional household tap connection (Part) including supply of 15mm dia PVC pipe of average length of 15 m, 10mm dia Gun-Metal Ferrule, Saddle piece (as required size) 15mm dia Bib cock etc. all complete from Paschim Bhatjangla Zone - II W/S scheme (Phase - I) of Retrofitting in Nadia District under Nadia Division P.H.E. Dte." (PART- A) | Assistant Engineer |  | ORD/000020/2021-2022 | 2154/ND | 21/05/2021 | 20/07/2021 | SAKTI ENTERPRISE | 33.45 | 51.22 | 153.15 | 100
Total | [13 empty] | 98.54 | 67.2 | 68.19