## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Division | Providing FHTC at Surface Water based Water Supply Scheme (Northern Sector), Part-II, Zone-IX within Nakashipara Block (Phase-C) | SM/08137 | Retrofitting | PROVIDING FHTC AT SURFACE WATER BASED W/S SCHEME N/ SECTOR PART-2, Z-9, NAKASHIPARA BLOCK, PHASE--C |  |  | VCH/000605/2021-2022 | 262/PFMS | 08/10/2021 | 08/10/2021 | TARUN KUMAR BHATTACHARYA | 84.44 | 0 | 0 | 0
2 | NADIA |  | Nadia Division | Providing FHTC at Surface Water based Water Supply Scheme (Northern Sector), Part-II, Zone-IX within Nakashipara Block (Phase-C) | SM/08137 | Retrofitting | Providing FHTC at Surface Water Based Water Supply Scheme (Northern Sector), Part-II, Zone-IX within Nakashipara Block ( Phase -C) in Nadia District under Nadia Division P.H.E. Dte Sl.No.3 | Assistant Engineer | Junior Engineer 2 | ORD/000475/2020-2021 | 889/ND | 19/02/2021 | 20/05/2021 | TARUN KUMAR BHATTACHARYA | 96.89 | 0 | 0 | 0
3 | NADIA |  | Nadia Division | Providing FHTC at Surface Water based Water Supply Scheme (Northern Sector), Part-II, Zone-IX within Nakashipara Block (Phase-C) | SM/08137 | Retrofitting | Laying additional distribution pipeline for providing FHTC at zone- Nagla, Raripara, Badbelgao, Bholadangavilleges under VI & IX , Part- II , Surface water based Water Supply Scheme, Nadia Northern Sector , Nakashipara Block | Assistant Engineer |  | ORD/000809/2021-2022 | 159/DSD | 17/03/2022 | 16/04/2022 | MAHAVIR PUMPS MFG PVT. LTD. | 4.24 | 0 | 0 | 0
4 | NADIA |  | Nadia Division | Providing FHTC at Surface Water based Water Supply Scheme (Northern Sector), Part-II, Zone-IX within Nakashipara Block (Phase-C) | SM/08137 | Retrofitting | Laying additional distribution pipeline for providing FHTC at Dogachhia, Deluigachi, Jalsukha and Saligram villages of zone VI & IX , Part- II , Surface water based Water Supply Scheme, Nadia Northern Sector , Nakashipara Block. | Assistant Engineer |  | ORD/000810/2021-2022 | 160/DSD | 17/03/2022 | 16/04/2022 | MAHAVIR PUMPS MFG PVT. LTD. | 3.92 | 0 | 0 | 0
5 | NADIA |  | Nadia Division | Providing FHTC at Surface Water based Water Supply Scheme (Northern Sector), Part-II, Zone-IX within Nakashipara Block (Phase-C) | SM/08137 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000086/2022-2023 | 4273/ND | 29/09/2022 | 29/09/2022 | Resource Division | 12.54 | 0 | 0 | 0
Total | [13 empty] | 202.02 | 0 | 0