## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Division | Providing Functional House Tap Connection from Dafarpota Zone I Water Supply Scheme (Phase-I) of Retrofitting under JalSwapna Program in Nadia District under Nadia Division, P.H.EDte. | SM/08665 | Retrofitting | Providing Functional House Tap Connection from Dafarpota Zone I Water Supply Scheme (Phase-I) of Retrofitting under JalSwapna Program in Nadia District under Nadia Division, P.H.EDte. |  |  | VCH/001013/2021-2022 | 606/PFMS | 11/03/2022 | 11/03/2022 | OTHERS | 6.11 | 0 | 0 | 0
2 | NADIA |  | Nadia Division | Providing Functional House Tap Connection from Dafarpota Zone I Water Supply Scheme (Phase-I) of Retrofitting under JalSwapna Program in Nadia District under Nadia Division, P.H.EDte. | SM/08665 | Retrofitting | Providing functional household tap connection (Part) including supply of 15mm dia PVC pipe of average length of 15 m, 10mm dia Gun Metal Ferrule, Saddle piece (as required size) 15mm dia Bib cock etc. all complete from Daforpota (Zone-I) W/S scheme in Nadia District under Nadia Division, PHE Dte. (Phase-I, Retrofitting) (Part-A) | Assistant Engineer |  | ORD/000200/2021-2022 | 5145/ND | 15/09/2021 | 29/11/2021 | SOMNATH CHATTERJEE | 63.36 | 0 | 0 | 0
3 | NADIA |  | Nadia Division | Providing Functional House Tap Connection from Dafarpota Zone I Water Supply Scheme (Phase-I) of Retrofitting under JalSwapna Program in Nadia District under Nadia Division, P.H.EDte. | SM/08665 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000070/2021-2022 | 803/ND | 18/02/2022 | 18/02/2022 | Resource Division | 6.6 | 0 | 0 | 0
4 | NADIA |  | Nadia Division | Providing Functional House Tap Connection from Dafarpota Zone I Water Supply Scheme (Phase-I) of Retrofitting under JalSwapna Program in Nadia District under Nadia Division, P.H.EDte. | SM/08665 | Retrofitting | Providing balance FHTC Of Retrofitting (Phase-I) Under JJM in Ground Based piped water supply scheme at Dafarpota Zone I to accommodate FHTC within Krishnagar I block under Krishnanagar Sub-Division under Nadia Division,PHE Dte. | Assistant Engineer |  | ORD/000056/2024-2025 | 3896/ND | 16/07/2024 | 14/09/2024 | SINGHA ROY & CO. | 34.11 | 0 | 0 | 0
5 | NADIA |  | Nadia Division | Providing Functional House Tap Connection from Dafarpota Zone I Water Supply Scheme (Phase-I) of Retrofitting under JalSwapna Program in Nadia District under Nadia Division, P.H.EDte. | SM/08665 | Retrofitting | Hiring of 1 (One) no Diesel Cab having contract permit from regional transport authority for office use of the Executive Engineer, Nadia Division, P.H.E. Dte. for a period of 183 ( One Hundred Eighty Three) Days on (F.N). | Assistant Engineer |  | ORD/000453/2023-2024 | 689/KLYSD-I | 01/06/2023 | 01/12/2023 | AVINABA ENGINEERING CONCERN | 2.4 | 0 | 0 | 100
Total | [13 empty] | 112.58 | 0 | 0