## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Division | Providing Functional House Tap Connection from Naserkuli Zone-I Water Supply Scheme (Phase-I) of Retrofitting under Jal SwapnaProgram in Nadia District under Nadia Division, P.H.E Dte. | SM/08667 | Retrofitting | Providing Functional House Tap Connection from Naserkuli Zone-I Water Supply Scheme (Phase-I) of Retrofitting under Jal SwapnaProgram in Nadia District under Nadia Division, P.H.E Dte. |  |  | VCH/000315/2022-2023 | 40/PFMS | 27/05/2022 | 27/05/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 1.04 | 0 | 0 | 0
2 | NADIA |  | Nadia Division | Providing Functional House Tap Connection from Naserkuli Zone-I Water Supply Scheme (Phase-I) of Retrofitting under Jal SwapnaProgram in Nadia District under Nadia Division, P.H.E Dte. | SM/08667 | Retrofitting | Providing Functional House Tap Connection from Naserkuli Zone-I Water Supply Scheme (Phase-I) of Retrofitting under Jal SwapnaProgram in Nadia District under Nadia Division, P.H.E Dte. |  |  | VCH/000314/2022-2023 | 39/PFMS | 27/05/2022 | 27/05/2022 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 4.36 | 0 | 0 | 0
3 | NADIA |  | Nadia Division | Providing Functional House Tap Connection from Naserkuli Zone-I Water Supply Scheme (Phase-I) of Retrofitting under Jal SwapnaProgram in Nadia District under Nadia Division, P.H.E Dte. | SM/08667 | Retrofitting | Hiring Diesel Luxury Car on daily basis (for12 months from 01.02.2022 to 31.01.2023) for the office use of the Assistant Engineer, Kalyani Sub - Division - II, P.H.E. Dte. | Assistant Engineer |  | ORD/000735/2021-2022 | 144/ Kly SD-II | 31/01/2022 | 31/01/2023 | SUMAN CHAKRABORTY | 4.8 | 0 | 0 | 65
4 | NADIA |  | Nadia Division | Providing Functional House Tap Connection from Naserkuli Zone-I Water Supply Scheme (Phase-I) of Retrofitting under Jal SwapnaProgram in Nadia District under Nadia Division, P.H.E Dte. | SM/08667 | Retrofitting | Hiring of Diesel car for official use in the office of the Assistant Engineer, Ranaghat Sub-Division, P.H. E. Dte., Kalyani, Nadia. Period of work 01-02-2023 to 31-07-2023= 183 days. | Assistant Engineer |  | ORD/000512/2022-2023 | 92/RSD | 01/02/2023 | 03/08/2023 | SUMAN CHAKRABORTY, A-7/40, KALYANI, NADIA | 3.2 | 0 | 0 | 25
5 | NADIA |  | Nadia Division | Providing Functional House Tap Connection from Naserkuli Zone-I Water Supply Scheme (Phase-I) of Retrofitting under Jal SwapnaProgram in Nadia District under Nadia Division, P.H.E Dte. | SM/08667 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000036/2021-2022 | 446/ND | 31/01/2022 | 31/01/2022 | Resource Division | 1.19 | 0 | 0 | 0
6 | NADIA |  | Nadia Division | Providing Functional House Tap Connection from Naserkuli Zone-I Water Supply Scheme (Phase-I) of Retrofitting under Jal SwapnaProgram in Nadia District under Nadia Division, P.H.E Dte. | SM/08667 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000075/2021-2022 | 821/ND | 18/02/2022 | 18/02/2022 | Resource Division | 5.5 | 0 | 0 | 0
7 | NADIA |  | Nadia Division | Providing Functional House Tap Connection from Naserkuli Zone-I Water Supply Scheme (Phase-I) of Retrofitting under Jal SwapnaProgram in Nadia District under Nadia Division, P.H.E Dte. | SM/08667 | Retrofitting | Providing functional household tap connection (Part) including supply of 15mm dia PVC pipe of average length of 15 m, Saddle piece (as required size) 15mm dia Bib cock etc. all complete from Naserkuli zone- I W/S scheme under Nadia Division, PHE Dte. | Assistant Engineer | Junior Engineer 4 | ORD/000199/2021-2022 | 5144/ND | 15/09/2021 | 14/12/2021 | DIAMOND ENGINEERS CO.OP SOCIETY LTD. | 87.52 | 0 | 0 | 100
Total | [13 empty] | 107.61 | 0 | 0