## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Division | Providing FHTC Surface Water Based Water Supply Scheme(Northern Sector), Part-I, Zone-V and VIII within Kaliganj Block.(Phase-C) | SM/08668 | Retrofitting | Providing FHTC at Surface Water Based Water Supply Scheme (Northern Sector) Part-I, Zone-V&VIII within Kaliganj Block (Phase-C) | Assistant Engineer | Junior Engineer 2 | ORD/000206/2021-2022 | 5180/ND | 20/09/2021 | 19/12/2021 | SATYABRATA CHAKRABORTY | 89.77 | 0 | 0 | 0
2 | NADIA |  | Nadia Division | Providing FHTC Surface Water Based Water Supply Scheme(Northern Sector), Part-I, Zone-V and VIII within Kaliganj Block.(Phase-C) | SM/08668 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000031/2022-2023 | 4292/ND | 29/09/2022 | 29/09/2022 | Resource Division | 12.54 | 0 | 0 | 0
3 | NADIA |  | Nadia Division | Providing FHTC Surface Water Based Water Supply Scheme(Northern Sector), Part-I, Zone-V and VIII within Kaliganj Block.(Phase-C) | SM/08668 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000177/2023-2024 | 312/ND | 15/01/2024 | 15/01/2024 | Resource Division | 2.62 | 0 | 0 | 0
4 | NADIA |  | Nadia Division | Providing FHTC Surface Water Based Water Supply Scheme(Northern Sector), Part-I, Zone-V and VIII within Kaliganj Block.(Phase-C) | SM/08668 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000178/2023-2024 | 313/ND | 15/01/2024 | 15/01/2024 | Resource Division | 5.4 | 0 | 0 | 0
5 | NADIA |  | Nadia Division | Providing FHTC Surface Water Based Water Supply Scheme(Northern Sector), Part-I, Zone-V and VIII within Kaliganj Block.(Phase-C) | SM/08668 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000184/2023-2024 | 319/ND | 15/01/2024 | 15/01/2024 | Resource Division | 12.55 | 0 | 0 | 0
Total | [13 empty] | 122.87 | 0 | 0