## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Division | Providing FHTC Surface Water Based Water Supply Scheme(Northern Sector), Part-II, Zone-VI within Nakashipara Block.(Phase-C) | SM/08669 | Retrofitting | Providing FHTC Surface Water Based Water Supply Scheme(Northern Sector), Part-II, Zone-VI within Nakashipara Block.(Phase-C) |  |  | VCH/000968/2021-2022 | 576/PFMS | 04/03/2022 | 04/03/2022 | TARUN KUMAR BHATTACHARYA | 21.16 | 0 | 0 | 0
2 | NADIA |  | Nadia Division | Providing FHTC Surface Water Based Water Supply Scheme(Northern Sector), Part-II, Zone-VI within Nakashipara Block.(Phase-C) | SM/08669 | Retrofitting | Providing FHTC Surface Water Based Water Supply Scheme(Northern Sector), Part-II, Zone-VI within Nakashipara Block.(Phase-C) |  |  | VCH/000908/2021-2022 | 548/PFMS | 23/02/2022 | 23/02/2022 | TARUN KUMAR BHATTACHARYA | 35 | 0 | 0 | 0
3 | NADIA |  | Nadia Division | Providing FHTC Surface Water Based Water Supply Scheme(Northern Sector), Part-II, Zone-VI within Nakashipara Block.(Phase-C) | SM/08669 | Retrofitting | Laying additional distribution pipeline for providing FHTC at zone-VI Phase- C, Part- II , Surface water based Water Supply Scheme, Nadia Northern Sector , Nakashipara Block. | Assistant Engineer |  | ORD/000815/2021-2022 | 47/DSD | 07/02/2022 | 22/02/2022 | TARUN KUMAR BHATTACHARYA | 2.19 | 1.12 | 51.31 | 0
4 | NADIA |  | Nadia Division | Providing FHTC Surface Water Based Water Supply Scheme(Northern Sector), Part-II, Zone-VI within Nakashipara Block.(Phase-C) | SM/08669 | Retrofitting | Providing FHTC at Surface Water Based Water Supply Scheme (Northern Sector) Part-II, Zone-VI within Nakashipara Block (Phase-C) | Assistant Engineer | Junior Engineer 1 | ORD/000208/2021-2022 | 5182/ND | 20/09/2021 | 19/12/2021 | TARUN KUMAR BHATTACHARYA | 86.53 | 23.52 | 27.18 | 100
5 | NADIA |  | Nadia Division | Providing FHTC Surface Water Based Water Supply Scheme(Northern Sector), Part-II, Zone-VI within Nakashipara Block.(Phase-C) | SM/08669 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000032/2022-2023 | 4275/ND | 29/09/2022 | 29/09/2022 | Resource Division | 0.02 | 0 | 0 | 0
Total | [13 empty] | 144.9 | 24.64 | 17.01