## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Division | Providing FHTC Surface Water Based Water Supply Scheme(Northern Sector), Part-II, Zone-IV within Nakashipara Block.(Phase-D) | SM/08670 | Retrofitting | Providing FHTC Surface Water Based Water Supply Scheme(Northern Sector), Part-II, Zone-IV within Nakashipara Block.(Phase-D) |  |  | VCH/000980/2021-2022 | 582/PFMS | 04/03/2022 | 04/03/2022 | SHYAMAL SHIL | 8.22 | 0 | 0 | 0
2 | NADIA |  | Nadia Division | Providing FHTC Surface Water Based Water Supply Scheme(Northern Sector), Part-II, Zone-IV within Nakashipara Block.(Phase-D) | SM/08670 | Retrofitting | Providing FHTC at Surface Water Based Water Supply Scheme (Northern Sector) Part-II, Zone-IV within Nakashipara Block (Phase-D) | Assistant Engineer | Junior Engineer 3 | ORD/000207/2021-2022 | 5181/ND | 20/09/2021 | 19/12/2021 | SHYAMAL SHIL | 89.79 | 0 | 0 | 0
3 | NADIA |  | Nadia Division | Providing FHTC Surface Water Based Water Supply Scheme(Northern Sector), Part-II, Zone-IV within Nakashipara Block.(Phase-D) | SM/08670 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000057/2021-2022 | 809/ND | 18/02/2022 | 18/02/2022 | Resource Division | 12.23 | 0 | 0 | 0
Total | [13 empty] | 110.23 | 0 | 0