## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Division | Providing Functional House Tap Connection from Dakshinpara Zone-I Water Supply Scheme under Jal Swapna Program in NadiaDistrict under Nadia Division, P.H.E Dte. (Phase-A) | SM/08674 | Retrofitting | Providing Functional House Tap Connection from Dakshinpara Zone-I Water Supply Scheme under Jal Swapna Program in NadiaDistrict under Nadia Division, P.H.E Dte. (Phase-A) |  |  | VCH/001011/2021-2022 | 606/PFMS | 11/03/2022 | 11/03/2022 | OTHERS | 8.13 | 0 | 0 | 0
2 | NADIA |  | Nadia Division | Providing Functional House Tap Connection from Dakshinpara Zone-I Water Supply Scheme under Jal Swapna Program in NadiaDistrict under Nadia Division, P.H.E Dte. (Phase-A) | SM/08674 | Retrofitting | Providing functional household tap connection (Part) including supply of 15mm dia PVC pipe of average length of 15 m, 10mm dia Gun-Metal Ferrule, Saddle piece (as required size) 15mm dia Bib cock etc. all complete for Dakshinpara Z-I Water Supply scheme Hanskhali block in Nadia District under Nadia Division P.H.E. Dte.(Phase-A) | Assistant Engineer |  | ORD/000203/2021-2022 | 5177/ND | 20/09/2021 | 19/12/2021 | M/S KALIMATA ENTERPRISE | 88.33 | 87.91 | 99.53 | 0
3 | NADIA |  | Nadia Division | Providing Functional House Tap Connection from Dakshinpara Zone-I Water Supply Scheme under Jal Swapna Program in NadiaDistrict under Nadia Division, P.H.E Dte. (Phase-A) | SM/08674 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000018/2021-2022 | 99/ND | 06/01/2022 | 06/01/2022 | Resource Division | 2.65 | 0 | 0 | 0
4 | NADIA |  | Nadia Division | Providing Functional House Tap Connection from Dakshinpara Zone-I Water Supply Scheme under Jal Swapna Program in NadiaDistrict under Nadia Division, P.H.E Dte. (Phase-A) | SM/08674 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000054/2021-2022 | 793/ND | 18/02/2022 | 18/02/2022 | Resource Division | 8.77 | 0 | 0 | 0
5 | NADIA |  | Nadia Division | Providing Functional House Tap Connection from Dakshinpara Zone-I Water Supply Scheme under Jal Swapna Program in NadiaDistrict under Nadia Division, P.H.E Dte. (Phase-A) | SM/08674 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000117/2021-2022 | 1035/ND | 03/03/2022 | 03/03/2022 | Resource Division | 15.16 | 0 | 0 | 0
Total | [13 empty] | 123.05 | 87.91 | 71.45