## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Division | Providing FHTC Surface Water Based Water Supply Scheme (Northern Sector) Part-II Zone-II within Nakashipara Block (Phase-B) | SM/08887 | Retrofitting | PROVIDING FHTC ..FROM NORTHRN SECTOR , PART-II, Z-II, PHASE-B, WITHIN NAKASHIPARA BLOCK W/S SCHEME |  |  | VCH/000874/2021-2022 | 471/PFMS | 02/02/2022 | 02/02/2022 | TARUN KUMAR BHATTACHARYA | 71.78 | 0 | 0 | 0
2 | NADIA |  | Nadia Division | Providing FHTC Surface Water Based Water Supply Scheme (Northern Sector) Part-II Zone-II within Nakashipara Block (Phase-B) | SM/08887 | Retrofitting | Providing FHTC Surface Water Based Water Supply Scheme (Northern Sector) Part-II Zone-II within Nakashipara Block (Phase-B) |  |  | VCH/000360/2022-2023 | 60/PFMS | 22/06/2022 | 22/06/2022 | TARUN KUMAR BHATTACHARYA | 5.49 | 0 | 0 | 0
3 | NADIA |  | Nadia Division | Providing FHTC Surface Water Based Water Supply Scheme (Northern Sector) Part-II Zone-II within Nakashipara Block (Phase-B) | SM/08887 | Retrofitting | Providing FHTC at Surface Water Based Water Supply Scheme (Northern Sector) Part-II, Zone-II within Nakashipara Block (Phase-B) | Assistant Engineer | Junior Engineer 1 | ORD/000244/2021-2022 | 5364/ND | 30/09/2021 | 29/12/2021 | TARUN KUMAR BHATTACHARYA | 86.48 | 0 | 0 | 100
4 | NADIA |  | Nadia Division | Providing FHTC Surface Water Based Water Supply Scheme (Northern Sector) Part-II Zone-II within Nakashipara Block (Phase-B) | SM/08887 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000042/2021-2022 | 451/ND | 31/01/2022 | 31/01/2022 | Resource Division | 3.98 | 0 | 0 | 0
5 | NADIA |  | Nadia Division | Providing FHTC Surface Water Based Water Supply Scheme (Northern Sector) Part-II Zone-II within Nakashipara Block (Phase-B) | SM/08887 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000033/2022-2023 | 4283/ND | 29/09/2022 | 29/09/2022 | Resource Division | 12.57 | 0 | 0 | 0
6 | NADIA |  | Nadia Division | Providing FHTC Surface Water Based Water Supply Scheme (Northern Sector) Part-II Zone-II within Nakashipara Block (Phase-B) | SM/08887 | Retrofitting | Collection of Household data through mobile app for FHTC Connection at following schemes under Nadia Division PHE Dte.Schemes: i) Naserkuli Zone-II ii) Subarna Behar Zone-I iii) Mahisunra Phase- I iv)Mahisunra Phase-II v)Bablari Dewanganj | Assistant Engineer | Junior Engineer 2 | ORD/000066/2023-2024 | 673/KlySd-I | 30/05/2023 | 30/11/2023 | HORIZEN | 4.62 | 0 | 0 | 100
7 | NADIA |  | Nadia Division | Providing FHTC Surface Water Based Water Supply Scheme (Northern Sector) Part-II Zone-II within Nakashipara Block (Phase-B) | SM/08887 | Retrofitting | Scheme Information Board at various water supply schemes under Nadia Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer 2 | ORD/000490/2023-2024 | 283/ND | 11/01/2024 | 11/03/2024 | BIBHAS PAL | 96.01 | 0 | 0 | 81
Total | [13 empty] | 280.93 | 0 | 0