## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Division | Proving FHTC (Functional Household Tap Connection ) by retrofitting under Jalswapno with utility shifting of water pipeline in connection to the work under Nadia highway Division I PWD (Roads)Dte along Dharmada-Muragaca Road 3.00 Kmp to 6.00kmp under Surf | SM/08889 | Retrofitting | Proving FHTC (Functional Household Tap Connection ) by retrofitting under Jalswapno with utility shifting of water pipeline in connection to the work under Nadia highway Division I PWD (Roads)Dte along Dharmada-Muragaca Road 3.00 Kmp to 6.00kmp under Surface water based water supply scheme (Northern Sector Part-III ) under Krishnagar Sub-division under Nadia Division, PH.E Dte. (Block- Krishnagar-II) |  |  | VCH/000915/2021-2022 | 555/PFMS | 23/02/2022 | 23/02/2022 | APURBA MANDAL | 67.83 | 0 | 0 | 0
2 | NADIA |  | Nadia Division | Proving FHTC (Functional Household Tap Connection ) by retrofitting under Jalswapno with utility shifting of water pipeline in connection to the work under Nadia highway Division I PWD (Roads)Dte along Dharmada-Muragaca Road 3.00 Kmp to 6.00kmp under Surf | SM/08889 | Retrofitting | Providing FHTC(functional household tap connection ) by retrofitting under''Jalswapno"with utility shifting of water pipeline in connection to the work under Nadia Highway Division -I PWD(Roads) Dte. along Dharmada-Muragachha road3.00 kmp to 6.00kmp under surface based Water Supply scheme(Northern sector part III) under Krishnagar sub-division under Nadia Divn,PHE Dte. | Assistant Engineer |  | ORD/000283/2021-2022 | 5695/ND | 03/11/2021 | 01/02/2022 | APURBA MANDAL | 75.34 | 0 | 0 | 100
3 | NADIA |  | Nadia Division | Proving FHTC (Functional Household Tap Connection ) by retrofitting under Jalswapno with utility shifting of water pipeline in connection to the work under Nadia highway Division I PWD (Roads)Dte along Dharmada-Muragaca Road 3.00 Kmp to 6.00kmp under Surf | SM/08889 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000002/2021-2022 | 6831/ND | 17/11/2021 | 17/11/2021 | Resource Division | 1.13 | 0 | 0 | 0
4 | NADIA |  | Nadia Division | Proving FHTC (Functional Household Tap Connection ) by retrofitting under Jalswapno with utility shifting of water pipeline in connection to the work under Nadia highway Division I PWD (Roads)Dte along Dharmada-Muragaca Road 3.00 Kmp to 6.00kmp under Surf | SM/08889 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000034/2022-2023 | 4310/ND | 29/09/2022 | 29/09/2022 | Resource Division | 8.09 | 0 | 0 | 0
5 | NADIA |  | Nadia Division | Proving FHTC (Functional Household Tap Connection ) by retrofitting under Jalswapno with utility shifting of water pipeline in connection to the work under Nadia highway Division I PWD (Roads)Dte along Dharmada-Muragaca Road 3.00 Kmp to 6.00kmp under Surf | SM/08889 | Retrofitting | Continuation of work order for Charges of entry of household data in JJM website along with Household Aadhar details and Geo-tagging the same along with a hard copy of the same in requisite format supplied by the department under Nadia Division, PHE Dte.w.e.f.01.12.2023 to 31.12.2023 | Assistant Engineer | Junior Engineer 2 | ORD/000456/2023-2024 | 1260/KLYSD-I | 30/11/2023 | 31/12/2023 | SUMAN CHAKRABORTY | 4.89 | 0 | 0 | 100
Total | [13 empty] | 157.27 | 0 | 0