## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Division | Providing FHTC Surface Water Based Water Supply Scheme(Northern Sector), Part-II, Zone-VII within Nakashipara Block.(Phase-C) | SM/08951 | Retrofitting | Providing Functional Household Tap connection(FHTC)at Surface Water Based Water Supply Scheme(Northern Sector) Part-II,Zone-VII within Nakashipara Block(Phase-C) | Assistant Engineer | Junior Engineer 1 | ORD/000384/2021-2022 | 7205/ND | 15/12/2021 | 15/03/2022 | CALCON CONSTRUCTION | 179.4 | 63.59 | 35.45 | 100
2 | NADIA |  | Nadia Division | Providing FHTC Surface Water Based Water Supply Scheme(Northern Sector), Part-II, Zone-VII within Nakashipara Block.(Phase-C) | SM/08951 | Retrofitting | Schedule for Laying additional distribution pipeline for providing FHTC at Dhnanajoypur, Dhaparia and Radhanagar villages under zone-VII , Part- II Phase C, Surface water based Water Supply Scheme, Nadia Northern Sector , Nakashipara Block. | Assistant Engineer |  | ORD/000061/2022-2023 | 175/B/DSD | 18/04/2022 | 18/05/2022 | CALCON CONSTRUCTIONS | 4.97 | 4.68 | 94.14 | 100
3 | NADIA |  | Nadia Division | Providing FHTC Surface Water Based Water Supply Scheme(Northern Sector), Part-II, Zone-VII within Nakashipara Block.(Phase-C) | SM/08951 | Retrofitting | Laying additional distribution pipeline for providing FHTC at Dhaparia, Dhananjoypur & Shibpur zone-VII , Part- II Phase C, Surface water based Water Supply Scheme, Nadia Northern Sector , Nakashipara Block. | Assistant Engineer |  | ORD/000817/2021-2022 | 49/DSD | 07/02/2022 | 22/02/2022 | CALCON CONSTRUCTIONS | 4.79 | 4.76 | 99.47 | 100
4 | NADIA |  | Nadia Division | Providing FHTC Surface Water Based Water Supply Scheme(Northern Sector), Part-II, Zone-VII within Nakashipara Block.(Phase-C) | SM/08951 | Retrofitting | Laying additional distribution pipeline for providing FHTC at Dhnanajoypur and Radhanagar villages under zone-VII , Part- II Phase C, Surface water based Water Supply Scheme, Nadia Northern Sector , Nakashipara Block. | Assistant Engineer |  | ORD/000818/2021-2022 | 50/DSD | 07/02/2022 | 22/02/2022 | CALCON CONSTRUCTIONS | 4.75 | 4.71 | 99.22 | 100
5 | NADIA |  | Nadia Division | Providing FHTC Surface Water Based Water Supply Scheme(Northern Sector), Part-II, Zone-VII within Nakashipara Block.(Phase-C) | SM/08951 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000061/2021-2022 | 795/ND | 18/02/2022 | 18/02/2022 | Resource Division | 7.22 | 0 | 0 | 0
6 | NADIA |  | Nadia Division | Providing FHTC Surface Water Based Water Supply Scheme(Northern Sector), Part-II, Zone-VII within Nakashipara Block.(Phase-C) | SM/08951 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000066/2021-2022 | 797/ND | 18/02/2022 | 18/02/2022 | Resource Division | 11 | 0 | 0 | 0
7 | NADIA |  | Nadia Division | Providing FHTC Surface Water Based Water Supply Scheme(Northern Sector), Part-II, Zone-VII within Nakashipara Block.(Phase-C) | SM/08951 | Retrofitting | Providing FHTC Surface Water Based Water Supply Scheme(Northern Sector), Part-II, Zone-VII within Nakashipara Block.(Phase-C) |  |  | VCH/001119/2021-2022 | 698/PFMS | 28/03/2022 | 28/03/2022 | CALCON CONSTRUCTIONS | 83.66 | 0 | 0 | 0
8 | NADIA |  | Nadia Division | Providing FHTC Surface Water Based Water Supply Scheme(Northern Sector), Part-II, Zone-VII within Nakashipara Block.(Phase-C) | SM/08951 | Retrofitting | Providing FHTC, Supplying, laying of distribution system including with all necessary specials, valves, UPVC/HDPE Pipes, 10 mm gun metal ferrule, saddle piece etc. & Construction of Manifold all complete for Zone- VII/B (Northern Sector Part-II) Under Nakashipara Block of Nadia District. | Assistant Engineer | Junior Engineer 2 | ORD/000313/2023-2024 | 4282/ND | 21/09/2023 | 03/12/2025 | SATYABRATA CHAKRABORTY | 397.18 | 0 | 0 | 14
Total | [13 empty] | 692.97 | 77.75 | 11.22