## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Division | Providing FHTC Surface Water Based Water Supply Scheme(Northern Sector), Part-II, Zone-VIII within Nakashipara Block.(Phase-C) | SM/08952 | Retrofitting | Providing FHTC Surface Water Based Water Supply Scheme(Northern Sector), Part-II, Zone-VIII within Nakashipara Block.(Phase-C) |  |  | VCH/000337/2022-2023 | 46/PFMS | 13/06/2022 | 13/06/2022 | MONDAL PRECISION PRIVATE LIMITED | 72.81 | 0 | 0 | 0
2 | NADIA |  | Nadia Division | Providing FHTC Surface Water Based Water Supply Scheme(Northern Sector), Part-II, Zone-VIII within Nakashipara Block.(Phase-C) | SM/08952 | Retrofitting | Laying additional distribution pipeline for providing FHTC at Digha, Birpur , sarbari & Patpukur villeges under zone VIII , Part-II , Surface water based Water Supply Scheme, Nadia Northern Sector , Nakashipara Block. | Assistant Engineer |  | ORD/000066/2022-2023 | 309/DSD | 27/07/2022 | 26/08/2022 | MONDAL PRECISION PRIVATE LIMITED | 4.78 | 0 | 0 | 0
3 | NADIA |  | Nadia Division | Providing FHTC Surface Water Based Water Supply Scheme(Northern Sector), Part-II, Zone-VIII within Nakashipara Block.(Phase-C) | SM/08952 | Retrofitting | Laying additional distribution pipeline for providing FHTC at Birpur Patpukur Teghari villeges under zone VIII , Part-II , Surface water based Water Supply Scheme, Nadia Northern Sector , Nakashipara Block. | Assistant Engineer |  | ORD/000067/2022-2023 | 310/DSD | 27/07/2022 | 26/08/2022 | MONDAL PRECISION PRIVATE LIMITED | 4.77 | 0 | 0 | 0
4 | NADIA |  | Nadia Division | Providing FHTC Surface Water Based Water Supply Scheme(Northern Sector), Part-II, Zone-VIII within Nakashipara Block.(Phase-C) | SM/08952 | Retrofitting | Laying additional distribution pipeline for providing FHTC at Birpur Petuabhanga & Digha villeges under zone VIII , Part-II , Surface water based Water Supply Scheme, Nadia Northern Sector , Nakashipara Block. | Assistant Engineer |  | ORD/000068/2022-2023 | 311/DSD | 27/07/2022 | 26/08/2022 | MONDAL PRECISION PRIVATE LIMITED | 4.84 | 0 | 0 | 0
5 | NADIA |  | Nadia Division | Providing FHTC Surface Water Based Water Supply Scheme(Northern Sector), Part-II, Zone-VIII within Nakashipara Block.(Phase-C) | SM/08952 | Retrofitting | Laying additional distribution pipeline for providing FHTC at Sarbari & Digha villeges under zone VIII , Part-II , Surface water based Water Supply Scheme, Nadia Northern Sector , Nakashipara Block. | Assistant Engineer |  | ORD/000069/2022-2023 | 312/DSD | 27/07/2022 | 26/08/2022 | MONDAL PRECISION PRIVATE LIMITED | 4.85 | 0 | 0 | 0
6 | NADIA |  | Nadia Division | Providing FHTC Surface Water Based Water Supply Scheme(Northern Sector), Part-II, Zone-VIII within Nakashipara Block.(Phase-C) | SM/08952 | Retrofitting | Providing Functional Household Tap Connection (FHTC) at Surface Water based Water Supply Scheme (Northern Sector) Part-II,Zone-VIII within Nakashipara Block(Phase-C) | Assistant Engineer | Junior Engineer 1 | ORD/000418/2021-2022 | 7315/ND | 21/12/2021 | 21/03/2022 | MONDAL PRECISION PRIVATE LIMITED | 180.04 | 0 | 0 | 100
7 | NADIA |  | Nadia Division | Providing FHTC Surface Water Based Water Supply Scheme(Northern Sector), Part-II, Zone-VIII within Nakashipara Block.(Phase-C) | SM/08952 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000084/2022-2023 | 4272/ND | 29/09/2022 | 29/09/2022 | Resource Division | 24.89 | 0 | 0 | 0
8 | NADIA |  | Nadia Division | Providing FHTC Surface Water Based Water Supply Scheme(Northern Sector), Part-II, Zone-VIII within Nakashipara Block.(Phase-C) | SM/08952 | Retrofitting | Providing FHTC at Surface Water Based Water Supply Scheme (Northern Sector),Part-II, Zone-V within Nakashipara Block(Phase-B) in Nadia District under Nadia Division P.H.E.Dte.(SL.3) | Assistant Engineer | Junior Engineer 3 | ORD/000461/2020-2021 | 868/ND | 18/02/2021 | 19/05/2021 | J.D.J. ENTERPRISE. A UNIT OF JDJ TRADERS PRIVET LIMITED | 97.09 | 0 | 0 | 0
9 | NADIA |  | Nadia Division | Providing FHTC Surface Water Based Water Supply Scheme(Northern Sector), Part-II, Zone-VIII within Nakashipara Block.(Phase-C) | SM/08952 | Retrofitting | Providing FHTC at Surface Water Based Water Supply Scheme (Northern Sector),Part-II, Zone-VI within Nakashipara Block(Phase-A) in Nadia District under Nadia Division P.H.E.Dte.(SL.4) | Assistant Engineer | Junior Engineer 3 | ORD/000474/2020-2021 | 888/ND | 19/02/2021 | 20/05/2021 | UNICON INDIA | 96.71 | 0 | 0 | 0
10 | NADIA |  | Nadia Division | Providing FHTC Surface Water Based Water Supply Scheme(Northern Sector), Part-II, Zone-VIII within Nakashipara Block.(Phase-C) | SM/08952 | Retrofitting | Providing FHTC, Supplying, laying of distribution system including with all necessary specials, valves, UPVC/HDPE Pipes, 10 mm gun metal ferrule, saddle piece etc. & Construction of Manifold all complete for Zone- VII/B (Northern Sector Part-II) Under Nakashipara Block of Nadia District. | Assistant Engineer | Junior Engineer 2 | ORD/000313/2023-2024 | 4282/ND | 21/09/2023 | 08/03/2025 | SATYABRATA CHAKRABORTY | 397.18 | 0 | 0 | 14
11 | NADIA |  | Nadia Division | Providing FHTC Surface Water Based Water Supply Scheme(Northern Sector), Part-II, Zone-VIII within Nakashipara Block.(Phase-C) | SM/08952 | Retrofitting | Providing FHTC, Supplying, laying of distribution system including with all necessary specials, valves, UPVC/HDPE Pipes, 10 mm gun metal ferrule, saddle piece etc. & Construction of Manifold all complete for Zone- III/A, III/B, VIII/A, VIII/B, VIII/C, IX/A & IX/B (Northern Sector Part-II) Under Nakashipara Block of Nadia District. | Assistant Engineer | Junior Engineer 2 | ORD/000355/2023-2024 | 4588/ND | 06/10/2023 | 26/09/2025 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 2304.9 | 0 | 0 | 19
12 | NADIA |  | Nadia Division | Providing FHTC Surface Water Based Water Supply Scheme(Northern Sector), Part-II, Zone-VIII within Nakashipara Block.(Phase-C) | SM/08952 | Retrofitting | Providing FHTC, Supplying, laying of distribution system including with all necessary specials, valves, UPVC/HDPE Pipes, 10 mm gun metal ferrule, saddle piece etc. & Construction of Manifold all complete for Zone- IV/A, IV/B, IV/C, VI/A & VI/B (Northern Sector Part-II) Under Nakashipara Block of Nadia District. | Assistant Engineer | Junior Engineer 3 | ORD/000356/2023-2024 | 4589/ND | 06/10/2023 | 26/09/2025 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 2427.03 | 0 | 0 | 50
Total | [13 empty] | 5619.88 | 0 | 0