## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Division | Providing FHTC Surface Water Based Water Supply Scheme(Northern Sector), Part-II, Zone-I, II and III within NakashiparaBlock. (Phase-C) | SM/08953 | Retrofitting | Providing FHTC Surface Water Based Water Supply Scheme(Northern Sector), Part-II, Zone-I, II and III within Nakashipara Block. (Phase-C) |  |  | VCH/001109/2021-2022 | 688/PFMS | 29/03/2022 | 29/03/2022 | ALOK ENTERPRISE (A UNIT OF SAKET TREXIM PVT. LTD.) | 51.63 | 0 | 0 | 0
2 | NADIA |  | Nadia Division | Providing FHTC Surface Water Based Water Supply Scheme(Northern Sector), Part-II, Zone-I, II and III within NakashiparaBlock. (Phase-C) | SM/08953 | Retrofitting | Providing FHTC Surface Water Based Water Supply Scheme(Northern Sector), Part-II, Zone-I, II and III within NakashiparaBlock. (Phase-C) |  |  | VCH/001108/2021-2022 | 680/PFMS | 25/03/2022 | 25/03/2022 | ALOK ENTERPRISE (A UNIT OF SAKET TREXIM PVT. LTD.) | 59 | 0 | 0 | 0
3 | NADIA |  | Nadia Division | Providing FHTC Surface Water Based Water Supply Scheme(Northern Sector), Part-II, Zone-I, II and III within NakashiparaBlock. (Phase-C) | SM/08953 | Retrofitting | Providing Functional Household Tap connection(FHTC)at Surface Water Based Water Supply Scheme(Northern Sector) Part-II,Zone-I,II &III within Nakashipara Block(Phase-C) | Assistant Engineer | Junior Engineer 2 | ORD/000383/2021-2022 | 7204/ND | 15/12/2021 | 15/03/2022 | ALOK ENTERPRISE (A UNIT OF SAKET TREXIM PVT. LTD.) | 189.26 | 0 | 0 | 100
4 | NADIA |  | Nadia Division | Providing FHTC Surface Water Based Water Supply Scheme(Northern Sector), Part-II, Zone-I, II and III within NakashiparaBlock. (Phase-C) | SM/08953 | Retrofitting | Laying additional distribution pipeline for providing FHTC at zone-I II & III, Part- II Phase C, Surface water based Water Supply Scheme, Nadia Northern Sector , Nakashipara Block. | Assistant Engineer |  | ORD/000819/2021-2022 | 51/DSD | 07/02/2022 | 22/02/2022 | ALOK ENTERPRISE (A UNIT OF SAKET TREXIM PVT. LTD.) | 4.85 | 0 | 0 | 100
5 | NADIA |  | Nadia Division | Providing FHTC Surface Water Based Water Supply Scheme(Northern Sector), Part-II, Zone-I, II and III within NakashiparaBlock. (Phase-C) | SM/08953 | Retrofitting | Laying additional distribution pipeline for providing FHTC at zone-I II & III, Part- II Phase C, Surface water based Water Supply Scheme, Nadia Northern Sector , Nakashipara Block. | Assistant Engineer |  | ORD/000821/2021-2022 | 53/DSD | 07/02/2022 | 22/02/2022 | ALOK ENTERPRISE (A UNIT OF SAKET TREXIM PVT. LTD.) | 4.68 | 0 | 0 | 100
6 | NADIA |  | Nadia Division | Providing FHTC Surface Water Based Water Supply Scheme(Northern Sector), Part-II, Zone-I, II and III within NakashiparaBlock. (Phase-C) | SM/08953 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000067/2021-2022 | 800/ND | 18/02/2022 | 18/02/2022 | Resource Division | 22.04 | 0 | 0 | 0
7 | NADIA |  | Nadia Division | Providing FHTC Surface Water Based Water Supply Scheme(Northern Sector), Part-II, Zone-I, II and III within NakashiparaBlock. (Phase-C) | SM/08953 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000162/2023-2024 | 229/ND | 11/01/2024 | 11/01/2024 | Resource Division | 16.4 | 0 | 0 | 0
8 | NADIA |  | Nadia Division | Providing FHTC Surface Water Based Water Supply Scheme(Northern Sector), Part-II, Zone-I, II and III within NakashiparaBlock. (Phase-C) | SM/08953 | Retrofitting | Construction of OHR, repair and renovation of staff room, repair of boundary wall, construction of service road and restoration of bituminous road. etc. of Surface Water Based Water Supply Scheme for Zone-III / B (Northern Sector Part-II) in Nakashipara Block of Nadia District to accomodate FHTC under Nadia Division, P.H.E. Dte. [SM/11839]. | Assistant Engineer | Junior Engineer 3 | ORD/000443/2023-2024 | 6112/ND | 21/12/2023 | 20/12/2026 | MONDAL ENTERPRISE | 201.12 | 0 | 0 | 5
Total | [13 empty] | 548.98 | 0 | 0