## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Division | Providing FHTC Surface Water Based Water Supply Scheme(Northern Sector), Part-II, Zone-V within Nakashipara Block.(Phase-C) | SM/08954 | Retrofitting | Providing Functional Household Tap Connection(FHTC) at Surface Water Based Water Supply Scheme(Northern Sector) Part-II,Zone-VA & VB within NAKASHIPARA BLOCK(PHASE-C) | Assistant Engineer | Junior Engineer 1 | ORD/000326/2021-2022 | 7051/ND | 06/12/2021 | 06/03/2022 | GHOSH BROTHERS | 179.71 | 154.65 | 86.06 | 100
2 | NADIA |  | Nadia Division | Providing FHTC Surface Water Based Water Supply Scheme(Northern Sector), Part-II, Zone-V within Nakashipara Block.(Phase-C) | SM/08954 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000040/2021-2022 | 455/ND | 31/01/2022 | 31/01/2022 | Resource Division | 1.49 | 0 | 0 | 0
3 | NADIA |  | Nadia Division | Providing FHTC Surface Water Based Water Supply Scheme(Northern Sector), Part-II, Zone-V within Nakashipara Block.(Phase-C) | SM/08954 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000083/2022-2023 | 4280/ND | 29/09/2022 | 29/09/2022 | Resource Division | 24.76 | 0 | 0 | 0
4 | NADIA |  | Nadia Division | Providing FHTC Surface Water Based Water Supply Scheme(Northern Sector), Part-II, Zone-V within Nakashipara Block.(Phase-C) | SM/08954 | Retrofitting | Continuation work for Wall Writing Work under Nadia Division P. H. Engineering Dte. | Assistant Engineer |  | ORD/000722/2024-2025 | 7571/ND | 27/12/2024 | 27/01/2025 | IMAGIN | 34.21 | 0 | 0 | 0
5 | NADIA |  | Nadia Division | Providing FHTC Surface Water Based Water Supply Scheme(Northern Sector), Part-II, Zone-V within Nakashipara Block.(Phase-C) | SM/08954 | Retrofitting | Collection of Household data through mobile app for FHTC Connection (Phase-X), under Nadia Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer 2 | ORD/000801/2024-2025 | 149/KlySD-I | 28/01/2025 | 25/01/2026 | TECHVISION | 4.86 | 0 | 0 | 70
6 | NADIA |  | Nadia Division | Providing FHTC Surface Water Based Water Supply Scheme(Northern Sector), Part-II, Zone-V within Nakashipara Block.(Phase-C) | SM/08954 | Retrofitting | Collection of Household data through mobile app for FHTC Connection (Phase-IX) under Nadia Division, P.H.E. Dte | Assistant Engineer | Junior Engineer 2 | ORD/000800/2024-2025 | 148/KlySD-I | 28/01/2025 | 28/07/2025 | TECHVISION | 4.86 | 0 | 0 | 100
7 | NADIA |  | Nadia Division | Providing FHTC Surface Water Based Water Supply Scheme(Northern Sector), Part-II, Zone-V within Nakashipara Block.(Phase-C) | SM/08954 | Retrofitting | Regarding restoration works of plassey Monument Road from 1.4km to 2.8km (left side) |  |  | BILL/00921/2024-2025 | BP-2024-025-374 | 18/03/2025 | 18/03/2025 | EXECUTIVE ENGINEER, NADIA HIGHWAY DIVISION NO-I, P.W. (ROADS) DIRECTORATE | 2.34 | 0 | 0 | 0
Total | [13 empty] | 252.23 | 154.65 | 61.32