## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Division | Providing FHTC Surface Water Based Water Supply Scheme(Northern Sector), Part-II, Zone-V within Nakashipara Block.(Phase-C) | SM/08954 | Retrofitting | Providing Functional Household Tap Connection(FHTC) at Surface Water Based Water Supply Scheme(Northern Sector) Part-II,Zone-VA & VB within NAKASHIPARA BLOCK(PHASE-C) | Assistant Engineer | Junior Engineer 1 | ORD/000326/2021-2022 | 7051/ND | 06/12/2021 | 06/03/2022 | GHOSH BROTHERS | 179.71 | 154.65 | 86.06 | 100
2 | NADIA |  | Nadia Division | Providing FHTC Surface Water Based Water Supply Scheme(Northern Sector), Part-II, Zone-V within Nakashipara Block.(Phase-C) | SM/08954 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000040/2021-2022 | 455/ND | 31/01/2022 | 31/01/2022 | Resource Division | 1.49 | 0 | 0 | 0
3 | NADIA |  | Nadia Division | Providing FHTC Surface Water Based Water Supply Scheme(Northern Sector), Part-II, Zone-V within Nakashipara Block.(Phase-C) | SM/08954 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000083/2022-2023 | 4280/ND | 29/09/2022 | 29/09/2022 | Resource Division | 24.76 | 0 | 0 | 0
4 | NADIA |  | Nadia Division | Providing FHTC Surface Water Based Water Supply Scheme(Northern Sector), Part-II, Zone-V within Nakashipara Block.(Phase-C) | SM/08954 | Retrofitting | Continuation work for Wall Writing Work under Nadia Division P. H. Engineering Dte. | Assistant Engineer |  | ORD/000722/2024-2025 | 7571/ND | 27/12/2024 | 27/01/2025 | IMAGIN | 34.21 | 0 | 0 | 0
Total | [13 empty] | 240.18 | 154.65 | 64.39