## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Division | Providing FHTC Surface Water Based Water Supply Scheme(Northern Sector), Part-I, Zone-VII within Kaliganj Block. (PhaseC) | SM/08955 | Retrofitting | Providing Functional Household Tap Connection (FHTC) at Surface Water Based Water Supply Scheme (northern Sector)Part-I,Zone-VII within Kaliganj Block (Phase-C) | Assistant Engineer |  | ORD/000417/2021-2022 | 7314/ND | 21/12/2021 | 21/03/2022 | ORIENT CONSTRUCTION | 180.23 | 0 | 0 | 0
2 | NADIA |  | Nadia Division | Providing FHTC Surface Water Based Water Supply Scheme(Northern Sector), Part-I, Zone-VII within Kaliganj Block. (PhaseC) | SM/08955 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000030/2022-2023 | 4291/ND | 29/09/2022 | 29/09/2022 | Resource Division | 24.87 | 0 | 0 | 0
3 | NADIA |  | Nadia Division | Providing FHTC Surface Water Based Water Supply Scheme(Northern Sector), Part-I, Zone-VII within Kaliganj Block. (PhaseC) | SM/08955 | Retrofitting | Providing FHTC, Supplying, laying of distribution system including with all necessary specials, valves, UPVC/HDPE Pipes, 10 mm gun metal ferrule, saddle piece etc. & Construction of Manifold all complete for Zone- IV/A, IV/B, IV/C, VI/A & VI/B (Northern Sector Part-II) Under Nakashipara Block of Nadia District. | Assistant Engineer | Junior Engineer 3 | ORD/000356/2023-2024 | 4589/ND | 06/10/2023 | 20/09/2026 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 2427.03 | 0 | 0 | 50
4 | NADIA |  | Nadia Division | Providing FHTC Surface Water Based Water Supply Scheme(Northern Sector), Part-I, Zone-VII within Kaliganj Block. (PhaseC) | SM/08955 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000176/2023-2024 | 311/ND | 15/01/2024 | 15/01/2024 | Resource Division | 18.65 | 0 | 0 | 0
Total | [13 empty] | 2650.78 | 0 | 0