## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Division | Providing FHTC Surface Water Based Water Supply Scheme(Northern Sector), Part-I, Zone-I, II AND IV within Kaliganj Block.(Phase-C) | SM/08956 | Retrofitting | Providing FHTC Surface Water Based Water Supply Scheme(Northern Sector), Part-I, Zone-I, II AND IV within Kaliganj Block.(Phase-C) |  |  | VCH/001085/2021-2022 | 653/PFMS | 21/03/2022 | 21/03/2022 | JAL PRAVAHIKA PRIVATE LIMITED | 55 | 0 | 0 | 0
2 | NADIA |  | Nadia Division | Providing FHTC Surface Water Based Water Supply Scheme(Northern Sector), Part-I, Zone-I, II AND IV within Kaliganj Block.(Phase-C) | SM/08956 | Retrofitting | Providing FHTC Surface Water Based Water Supply Scheme(Northern Sector), Part-I, Zone-I, II AND IV within Kaliganj Block.(Phase-C) |  |  | VCH/001096/2021-2022 | 664/PFMS | 23/03/2022 | 23/03/2022 | JAL PRAVAHIKA PRIVATE LIMITED | 42.43 | 0 | 0 | 0
3 | NADIA |  | Nadia Division | Providing FHTC Surface Water Based Water Supply Scheme(Northern Sector), Part-I, Zone-I, II AND IV within Kaliganj Block.(Phase-C) | SM/08956 | Retrofitting | Providing FHTC Surface Water Based Water Supply Scheme(Northern Sector), Part-I, Zone-I, II AND IV within Kaliganj Block.(Phase-C) |  |  | VCH/000208/2022-2023 | 33/PFMS | 23/05/2022 | 23/05/2022 | JAL PRAVAHIKA PRIVATE LIMITED | 50.46 | 0 | 0 | 0
4 | NADIA |  | Nadia Division | Providing FHTC Surface Water Based Water Supply Scheme(Northern Sector), Part-I, Zone-I, II AND IV within Kaliganj Block.(Phase-C) | SM/08956 | Retrofitting | Providing Functional Household Tap Connection (FHTC) at Surface Water Based Water Supply Scheme (Northern Sector) Part-I, Zone-I,II & IV within KALIGANJ BLOCK(Phase-C) | Assistant Engineer | Junior Engineer 2 | ORD/000327/2021-2022 | 7050/ND | 06/12/2021 | 06/03/2022 | JAL PRAVAHIKA PRIVATE LIMITED | 180.28 | 26.9 | 14.92 | 100
5 | NADIA |  | Nadia Division | Providing FHTC Surface Water Based Water Supply Scheme(Northern Sector), Part-I, Zone-I, II AND IV within Kaliganj Block.(Phase-C) | SM/08956 | Retrofitting | Laying additional distribution pipeline for providing FHTC at Ballavpara, Basatpur, Kanua, Juranpur Bhagyabantapur, Gobra zone-I & II , Part- I Phase C, Surface water based Water Supply Scheme, Nadia Northern Sector , Kaliganj Block. | Assistant Engineer |  | ORD/000062/2022-2023 | 175/C/DSD | 18/04/2022 | 18/05/2022 | JAL PRAVAHIKA PRIVATE LIMITED | 4.85 | 4.8 | 98.87 | 100
6 | NADIA |  | Nadia Division | Providing FHTC Surface Water Based Water Supply Scheme(Northern Sector), Part-I, Zone-I, II AND IV within Kaliganj Block.(Phase-C) | SM/08956 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000038/2021-2022 | 428/ND | 31/01/2022 | 31/01/2022 | Resource Division | 1.99 | 0 | 0 | 0
7 | NADIA |  | Nadia Division | Providing FHTC Surface Water Based Water Supply Scheme(Northern Sector), Part-I, Zone-I, II AND IV within Kaliganj Block.(Phase-C) | SM/08956 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000085/2021-2022 | 817/ND | 18/02/2022 | 18/02/2022 | Resource Division | 10.98 | 0 | 0 | 0
8 | NADIA |  | Nadia Division | Providing FHTC Surface Water Based Water Supply Scheme(Northern Sector), Part-I, Zone-I, II AND IV within Kaliganj Block.(Phase-C) | SM/08956 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000044/2021-2022 | 447/ND | 31/01/2022 | 31/01/2022 | Resource Division | 1.99 | 0 | 0 | 0
9 | NADIA |  | Nadia Division | Providing FHTC Surface Water Based Water Supply Scheme(Northern Sector), Part-I, Zone-I, II AND IV within Kaliganj Block.(Phase-C) | SM/08956 | Retrofitting | Scheme Information Board at various water supply schemes under Nadia Division, P.H.E. Dte. | Assistant Engineer | Junior Engineer 2 | ORD/000490/2023-2024 | 283/ND | 11/01/2024 | 11/03/2024 | BIBHAS PAL | 96.01 | 5.03 | 5.23 | 81
10 | NADIA |  | Nadia Division | Providing FHTC Surface Water Based Water Supply Scheme(Northern Sector), Part-I, Zone-I, II AND IV within Kaliganj Block.(Phase-C) | SM/08956 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000172/2023-2024 | 307/ND | 15/01/2024 | 15/01/2024 | Resource Division | 12.39 | 0 | 0 | 0
11 | NADIA |  | Nadia Division | Providing FHTC Surface Water Based Water Supply Scheme(Northern Sector), Part-I, Zone-I, II AND IV within Kaliganj Block.(Phase-C) | SM/08956 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000169/2023-2024 | 304/ND | 15/01/2024 | 15/01/2024 | Resource Division | 23.27 | 0 | 0 | 0
12 | NADIA |  | Nadia Division | Providing FHTC Surface Water Based Water Supply Scheme(Northern Sector), Part-I, Zone-I, II AND IV within Kaliganj Block.(Phase-C) | SM/08956 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000168/2023-2024 | 303/ND | 15/01/2024 | 15/01/2024 | Resource Division | 10.96 | 0 | 0 | 0
13 | NADIA |  | Nadia Division | Providing FHTC Surface Water Based Water Supply Scheme(Northern Sector), Part-I, Zone-I, II AND IV within Kaliganj Block.(Phase-C) | SM/08956 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000170/2023-2024 | 305/ND | 15/01/2024 | 15/01/2024 | Resource Division | 3.81 | 0 | 0 | 0
14 | NADIA |  | Nadia Division | Providing FHTC Surface Water Based Water Supply Scheme(Northern Sector), Part-I, Zone-I, II AND IV within Kaliganj Block.(Phase-C) | SM/08956 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000171/2023-2024 | 306/ND | 15/01/2024 | 15/01/2024 | Resource Division | 8.98 | 0 | 0 | 0
15 | NADIA |  | Nadia Division | Providing FHTC Surface Water Based Water Supply Scheme(Northern Sector), Part-I, Zone-I, II AND IV within Kaliganj Block.(Phase-C) | SM/08956 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000183/2023-2024 | 318/ND | 15/01/2024 | 15/01/2024 | Resource Division | 3.27 | 0 | 0 | 0
Total | [13 empty] | 506.67 | 36.73 | 7.25