## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Division | Providing FHTC Surface Water Based Water Supply Scheme(Northern Sector), Part-I, Zone-III and IX within Kaliganj Block.(Phase-D) | SM/08957 | Retrofitting | Providing Functional Household Tap Connection(FHTC) at Surface Water Based Water Supply Scheme (Northern Sector) Part-I, Zone-III & IX within KALIGANJ BLOCK(Phase-D). | Assistant Engineer | Junior Engineer 3 | ORD/000325/2021-2022 | 7052/ND | 06/12/2021 | 06/03/2022 | TARUN KUMAR BHATTACHARYA | 180.22 | 0 | 0 | 0
2 | NADIA |  | Nadia Division | Providing FHTC Surface Water Based Water Supply Scheme(Northern Sector), Part-I, Zone-III and IX within Kaliganj Block.(Phase-D) | SM/08957 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000065/2021-2022 | 796/ND | 18/02/2022 | 18/02/2022 | Resource Division | 16.5 | 0 | 0 | 0
3 | NADIA |  | Nadia Division | Providing FHTC Surface Water Based Water Supply Scheme(Northern Sector), Part-I, Zone-III and IX within Kaliganj Block.(Phase-D) | SM/08957 | Retrofitting | Filling fine sand over upvc pipeline for road restoration work at nimtala juranpur road(both side of road) in connection with augmentation of surface water based w/s scheme for Arsenic affected areas of Nadia district( Northern sector part-I) under Nadia Division PHE Dte. | Assistant Engineer | Junior Engineer 1 | ORD/000003/2024-2025 | 918KlySD-I | 07/06/2024 | 22/06/2024 | UMWELT ENGINEER PVT LTD | 13.46 | 0 | 0 | 100
4 | NADIA |  | Nadia Division | Providing FHTC Surface Water Based Water Supply Scheme(Northern Sector), Part-I, Zone-III and IX within Kaliganj Block.(Phase-D) | SM/08957 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000181/2023-2024 | 316/ND | 15/01/2024 | 15/01/2024 | Resource Division | 7.11 | 0 | 0 | 0
5 | NADIA |  | Nadia Division | Providing FHTC Surface Water Based Water Supply Scheme(Northern Sector), Part-I, Zone-III and IX within Kaliganj Block.(Phase-D) | SM/08957 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000182/2023-2024 | 317/ND | 15/01/2024 | 15/01/2024 | Resource Division | 8.18 | 0 | 0 | 0
6 | NADIA |  | Nadia Division | Providing FHTC Surface Water Based Water Supply Scheme(Northern Sector), Part-I, Zone-III and IX within Kaliganj Block.(Phase-D) | SM/08957 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000180/2023-2024 | 315/ND | 15/01/2024 | 15/01/2024 | Resource Division | 16.25 | 0 | 0 | 0
7 | NADIA |  | Nadia Division | Providing FHTC Surface Water Based Water Supply Scheme(Northern Sector), Part-I, Zone-III and IX within Kaliganj Block.(Phase-D) | SM/08957 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000179/2023-2024 | 314/ND | 15/01/2024 | 15/01/2024 | Resource Division | 11.76 | 0 | 0 | 0
Total | [13 empty] | 253.48 | 0 | 0