## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Division | Providing FHTC Surface Water Based Water Supply Scheme(Northern Sector), Part-II, Zone-VI and IX within NakashiparaBlock. (Phase-D) | SM/08958 | Retrofitting | Providing Functional household Tap Connection (FHTC) at Surface Water Based Water Supply Scheme (Northern Sector) Part-II, Zone-VI & IX within Nakashipara Block (Phase-D) | Assistant Engineer | Junior Engineer 3 | ORD/000391/2021-2022 | 7255/ND | 17/12/2021 | 17/03/2022 | MAHAVIR PUMPS MFG PVT. LTD. | 180.19 | 74.78 | 41.5 | 100
2 | NADIA |  | Nadia Division | Providing FHTC Surface Water Based Water Supply Scheme(Northern Sector), Part-II, Zone-VI and IX within NakashiparaBlock. (Phase-D) | SM/08958 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000062/2021-2022 | 814/ND | 18/02/2022 | 18/02/2022 | Resource Division | 10.98 | 0 | 0 | 0
3 | NADIA |  | Nadia Division | Providing FHTC Surface Water Based Water Supply Scheme(Northern Sector), Part-II, Zone-VI and IX within NakashiparaBlock. (Phase-D) | SM/08958 | Retrofitting | Providing FHTC Surface Water Based Water Supply Scheme(Northern Sector), Part-II, Zone-VI and IX within NakashiparaBlock. (Phase-D) |  |  | VCH/000210/2022-2023 | 35/PFMS | 23/05/2022 | 23/05/2022 | MAHAVIR PUMPS MFG PVT. LTD. | 51.4 | 0 | 0 | 0
4 | NADIA |  | Nadia Division | Providing FHTC Surface Water Based Water Supply Scheme(Northern Sector), Part-II, Zone-VI and IX within NakashiparaBlock. (Phase-D) | SM/08958 | Retrofitting | Providing FHTC Surface Water Based Water Supply Scheme(Northern Sector), Part-II, Zone-VI and IX within NakashiparaBlock. (Phase-D) |  |  | VCH/001092/2021-2022 | 660/PFMS | 23/03/2022 | 23/03/2022 | MAHAVIR PUMPS MFG PVT. LTD. | 4.34 | 0 | 0 | 0
5 | NADIA |  | Nadia Division | Providing FHTC Surface Water Based Water Supply Scheme(Northern Sector), Part-II, Zone-VI and IX within NakashiparaBlock. (Phase-D) | SM/08958 | Retrofitting | Providing FHTC Surface Water Based Water Supply Scheme(Northern Sector), Part-II, Zone-VI and IX within NakashiparaBlock. (Phase-D) |  |  | VCH/001086/2021-2022 | 654/PFMS | 21/03/2022 | 21/03/2022 | MAHAVIR PUMPS MFG PVT. LTD. | 33 | 0 | 0 | 0
6 | NADIA |  | Nadia Division | Providing FHTC Surface Water Based Water Supply Scheme(Northern Sector), Part-II, Zone-VI and IX within NakashiparaBlock. (Phase-D) | SM/08958 | Retrofitting | Providing FHTC, Supplying, laying of distribution system including with all necessary specials, valves, UPVC/HDPE Pipes, 10 mm gun metal ferrule, saddle piece etc. & Construction of Manifold all complete for Zone- IV/A, IV/B, IV/C, VI/A & VI/B (Northern Sector Part-II) Under Nakashipara Block of Nadia District. | Assistant Engineer | Junior Engineer 3 | ORD/000356/2023-2024 | 4589/ND | 06/10/2023 | 20/09/2026 | SRIJAN ECOLOGICAL UPLIFTMENT PVT. LTD | 2427.03 | 0 | 0 | 50
7 | NADIA |  | Nadia Division | Providing FHTC Surface Water Based Water Supply Scheme(Northern Sector), Part-II, Zone-VI and IX within NakashiparaBlock. (Phase-D) | SM/08958 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000163/2023-2024 | 232/ND | 11/01/2024 | 11/01/2024 | Resource Division | 19.22 | 0 | 0 | 0
8 | NADIA |  | Nadia Division | Providing FHTC Surface Water Based Water Supply Scheme(Northern Sector), Part-II, Zone-VI and IX within NakashiparaBlock. (Phase-D) | SM/08958 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000165/2023-2024 | 233/ND | 11/01/2024 | 11/01/2024 | Resource Division | 20.91 | 0 | 0 | 0
Total | [13 empty] | 2747.07 | 74.78 | 2.72