## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | NADIA |  | Nadia Division | Providing FHTC Surface Water Based Water Supply Scheme(Northern Sector), Part-III, Zone-I, II AND III within Krishnagar-II and Nabadwip (Part) Block. (Phase-C) | SM/08960 | Retrofitting | Providing FHTC at Surface Water Based Water Supply Scheme (Northern Sector) Part-III, Zone-I,II & III within Krishnagar & Nabadwip(Part) Block (Phase-C) | Assistant Engineer |  | ORD/000282/2021-2022 | 5694/ND | 03/11/2021 | 01/02/2022 | MALLICK ENTERPRISE | 86.12 | 0 | 0 | 0
2 | NADIA |  | Nadia Division | Providing FHTC Surface Water Based Water Supply Scheme(Northern Sector), Part-III, Zone-I, II AND III within Krishnagar-II and Nabadwip (Part) Block. (Phase-C) | SM/08960 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000081/2022-2023 | 4302/ND | 29/09/2022 | 29/09/2022 | Resource Division | 12.75 | 0 | 0 | 0
3 | NADIA |  | Nadia Division | Providing FHTC Surface Water Based Water Supply Scheme(Northern Sector), Part-III, Zone-I, II AND III within Krishnagar-II and Nabadwip (Part) Block. (Phase-C) | SM/08960 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000139/2023-2024 | 293/ND | 15/01/2024 | 15/01/2024 | Resource Division | 10.84 | 0 | 0 | 0
4 | NADIA |  | Nadia Division | Providing FHTC Surface Water Based Water Supply Scheme(Northern Sector), Part-III, Zone-I, II AND III within Krishnagar-II and Nabadwip (Part) Block. (Phase-C) | SM/08960 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000140/2023-2024 | 294/ND | 15/01/2024 | 15/01/2024 | Resource Division | 20.53 | 0 | 0 | 0
5 | NADIA |  | Nadia Division | Providing FHTC Surface Water Based Water Supply Scheme(Northern Sector), Part-III, Zone-I, II AND III within Krishnagar-II and Nabadwip (Part) Block. (Phase-C) | SM/08960 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000141/2023-2024 | 295/ND | 15/01/2024 | 15/01/2024 | Resource Division | 19.84 | 0 | 0 | 0
6 | NADIA |  | Nadia Division | Providing FHTC Surface Water Based Water Supply Scheme(Northern Sector), Part-III, Zone-I, II AND III within Krishnagar-II and Nabadwip (Part) Block. (Phase-C) | SM/08960 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000146/2023-2024 | 300/ND | 15/01/2024 | 15/01/2024 | Resource Division | 4.4 | 0 | 0 | 0
Total | [13 empty] | 154.48 | 0 | 0